- Cybersecurity breach during IT system integration merging two banking platforms creates exploitable vulnerabilities

- Regulatory approval delay (OSFI/FCAC) complex deal involving a Schedule I bank acquiring a Loblaw-affiliated entity

- Customer attrition post-migration PC Financial customers may switch banks when rebranded away from Loblaw

- Data migration failure or corruption transferring customer records, loan files, and transaction history across systems

- Key talent loss PC Financial staff may exit during transition uncertainty

- Brand confusion / reputational damage customers unsure who holds their deposits after branding changes

- Integration cost overrun tech, legal, HR, and operational costs exceeding deal projections

- Loblaw co-dependency disruption PC Financial operates through Loblaw stores; exit from that relationship is operationally complex

- Cross-sell conversion failure EQB fails to upsell PC Financial customers into mortgages or other EQB products

- Interest rate sensitivity rising or volatile rates affect mortgage portfolio profitability post-acquisition

- Regulatory capital requirement changes OSFI could impose new capital buffers on the combined entity

- Third-party vendor/contract disputes Loblaw-side service agreements may not transfer cleanly to EQB

- Credit quality deterioration PC Financial's loan book may have higher default risk than disclosed

- PIPEDA / privacy compliance failures migrating personal data without full regulatory compliance

- Competitor poaching of PC Financial customers TD, RBC, or neobanks aggressively targeting customers during transition

- Operational downtime during system cutover banking services unavailable during migration windows

- Fraud spike during transition account takeovers or identity fraud exploiting the confusion period

- Inaccurate due diligence on loan portfolio quality hidden non-performing loans surface post-close

- Employee benefits / HR integration friction aligning compensation, benefits, and culture between two firms

- Liquidity risk from deposit runoff unexpected withdrawal surge if customer confidence wavers

- Loblaw relationship souring post-deal residual commercial dependencies create ongoing negotiation friction

- Foreign exchange risk minimal but present if any deal components are USD-denominated

- Legal challenges from PC Financial employees wrongful dismissal or class actions during workforce integration

- Adverse media coverage negative press during a stumble could amplify customer churn

- Mis-selling or product suitability complaints PC Financial customers mis-directed into EQB products they don't need

- Technology vendor lock-in EQB inherits legacy contracts that are expensive to exit

- Failure to meet synergy targets projected $X in cost savings or revenue uplift not materialized

- Anti-money laundering (AML) compliance gaps PC Financial's AML controls may not meet EQB's standards

- Change management fatigue internal teams overwhelmed by volume of integration workstreams

- Environmental/social reputational risk any ESG-related controversy during the deal attracts scrutiny

- Underestimating IT infrastructure age legacy PC Financial systems more outdated than assessed

- Loss of Loblaw co-branding benefits PC Points/loyalty program integration complexities hurting retention

- Geopolitical or macro shock recession, housing market crash affecting EQB's mortgage-heavy business

- Insurance and indemnity gaps deal reps & warranties coverage insufficient for undisclosed liabilities

- Governance integration lag PC Financial board/committee structures not dissolved cleanly, creating decision-making confusion