## I&W Analysis
ALY6130 Assignment 4 I&W Quantitative Risk Assessment ¦ EQB Inc. / PC Financial Acquisition ¦ Group 2
Indicators & Warnings (I&W) Analysis Five Priority Risks (R-01, R-02, R-03, R-04, R-05)
Risk ID | Risk Name | I&W Indicator | Warning Level | Probability (0–1) | Cost/Revenue Impact (CAD) | EMV (CAD) | Optimistic (CAD M) | Most Likely (CAD M) | Pessimistic (CAD M) | Risk Type
R-01 | Cybersecurity Breach During IT Integration | High/critical security incidents >=5/month in SOC | Red | 0.35 | 50000000 | 17500000 | 20 | 80 | 200 | Threat
R-01 |  | Confirmed unauthorized access to customer data | Red | 0.2 | 120000000 | 24000000 |  |  |  | Threat
R-01 |  | OSFI mandatory breach notification triggered | Critical | 0.15 | 180000000 | 27000000 |  |  |  | Threat
R-02 | Regulatory Approval Delay | 180-270 days elapsed without approval decision | Amber | 0.4 | 15000000 | 6000000 | 5 | 20 | 75 | Threat
R-02 |  | Regulator requests additional/supplemental filing | Amber | 0.3 | 8000000 | 2400000 |  |  |  | Threat
R-02 |  | Conditional approval imposing PC Optimum data restrictions | Red | 0.15 | 60000000 | 9000000 |  |  |  | Threat
R-03 | Customer Attrition from PC Financial Portfolio | Monthly churn rate > 3% among migrated customers | Amber | 0.45 | 30000000 | 13500000 | 10 | 35 | 90 | Threat
R-03 |  | NPS drops > 15 points within 60 days of migration | Amber | 0.35 | 20000000 | 7000000 |  |  |  | Threat
R-03 |  | Competitor launches loyalty-linked product targeting PC Optimum base | Red | 0.25 | 50000000 | 12500000 |  |  |  | Threat
R-04 | Fraud Spike During Integration | Monthly fraud incident rate increases > 40% vs. pre-integration baseline | Amber | 0.5 | 15000000 | 7500000 | 8 | 28 | 70 | Threat
R-04 |  | Account takeover complaints from PC Financial customers spike > 2x | Red | 0.35 | 25000000 | 8750000 |  |  |  | Threat
R-04 |  | Confirmed identity fraud losses exceed $1M in any single month | Red | 0.2 | 45000000 | 9000000 |  |  |  | Threat
R-05 | Cross-Sell Conversion Opportunity (★ Positive) | Monthly conversion trajectory on track for 15%+ cumulative at 18 months | Green | 0.6 | 80000000 | 48000000 | 180 | 100 | 30 | Opportunity
R-05 |  | EQ Bank app downloads among PC Financial cardholders grow MoM for 3+ months | Green | 0.65 | 40000000 | 26000000 |  |  |  | Opportunity
R-05 |  | PC Optimum-linked personalized offers achieve > 5% product open rate | Green | 0.5 | 60000000 | 30000000 |  |  |  | Opportunity
TOTAL THREAT EMV | [5 empty] | 144150000
TOTAL OPPORTUNITY EMV | [5 empty] | 104000000
NET POSITION=OPPORTUNITY -THREAT | [5 empty] | -40150000
Risk | Total EMV (CAD) | MC Mean (CAD) | MC Median (CAD) | Rec. Reserve | Type
R-01 | 68500000 | 57800000 | 57700000 | $100M | Threat
R-02 | 17400000 | 16200000 | 16200000 | $30M | Threat
R-03 | 33000000 | 25800000 | 25800000 | $50M | Threat
R-04 | 25250000 | 20400000 | 20300000 | $40M | Threat
R-05 | 104000000 | 83600000 | 83500000 | N/A (upside) | Opportunity
NET THREAT CONTINGENCY RESERVE | 144150000 | 120200000 | 120100000 | $120M+ | Threats only

## Risk Profile (RT & RP)
ALY6130 Assignment 4 — Updated Risk Profile (RT & RP) ¦ EQB Inc. / PC Financial Acquisition
Risk register updated with I&W quantitative values — Assignments 3 and 4 integrated
Risk # | Risk Name | L (1-9) | I (1-9) | Score (LxI) | Priority | I&W Prob. (0-1) | Cost/Revenue Impact (CAD) | EMV (CAD) | MC Mean (CAD M) | MC Median (CAD M) | Risk Treatment (Mitigation) | Risk Owner | Status
R-01 | Cybersecurity Breach During IT Integration | 9 | 9 | 81 | H | 0.23 | 80000000 | 18400000 | 57800000 | 57700000 | Activate dedicated cybersecurity workstream in IMO; deploy zero-trust architecture; conduct pre/post-migration access control audits; engage third-party penetration testing; establish OSFI B-10 breach notification protocol. | CISO / Integration Management Office | Open
R-02 | Regulatory Approval Delay by OSFI / Minister of Finance | 3 | 8 | 24 | M | 0.28 | 20000000 | 5600000 | 16200000 | 16200000 | Maintain proactive communication with OSFI and Competition Bureau; prepare contingency scenarios for 6-12 month delays; engage external regulatory counsel with Canadian bank M&A experience. | Chief Risk Officer / General Counsel | Open
R-03 | Customer Attrition from PC Financial Portfolio | 7 | 8 | 56 | H | 0.35 | 35000000 | 12250000 | 25800000 | 25800000 | Launch early customer communication campaign pre-close; deploy PC Optimum-linked personalized EQ Bank product offers within 90 days of close; monitor NPS and churn KPIs monthly. | CMO / Chief Customer Experience Officer | Open
R-17 | Fraud Spike During Integration — Account Takeover | 9 | 6 | 54 | H | 0.35 | 28000000 | 9800000 | 20400000 | 20300000 | Deploy real-time fraud detection across dual-system integration period; implement enhanced identity verification for PC Financial customer logins; establish dedicated fraud response team during migration window. | Chief Risk Officer / Fraud Prevention Lead | Open
R-38 | Cross-Sell Conversion Opportunity — PC Financial Credit-Card Customers (★ Positive Risk) | 9 | 9 | 81 | H | 0.58 | 100000000 | 58000000 | 83600000 | 83500000 | Launch structured cross-sell campaign within 90 days of deal close; use PC Optimum loyalty data for personalized product recommendations; apply PIPEDA-compliant consent frameworks; set quarterly conversion KPIs. | CMO / Chief Digital Officer | Open

## Formula for Ref
Probability of Occurrence |  | High (≥45)
Very Unlikely | 1 | Medium (21–44)
Somewhat unlikely | 3 | Low (≤20)
50-50 possibility | 5
Somewhat likely | 7
Very likely | 9
Impact of Risk
Very Low | 1
Somewhat Low | 2
Moderate | 4
Somewhat High | 6
High | 8
Extremely High | 9
Risk Score= Impact * Likelihood score
EMV =Prob *Cost Impact
I &W prob =avg of Prob(0-1)
Prob score defined according to each indiactor of the risk ,scenario based