## Complete RT RP
Risk Treatment and Response Plan (RT&RP) EQB Inc. Acquisition of PC Financial from Loblaw Companies Limited
Risk ID | Category | Risk Description | L | I | Score | Priority | Resulting In | Consequence / Impact | Response Strategy | Justification | Response Actions | Risk Owner | Date Identified | Status
R-01 | Operational / Cyber | Cybersecurity Breach During IT System Integration | 9 | 9 | 81 | H | Unauthorized access to 3.5M+ customer financial records, system outages, and OSFI B-13 enforcement actions across dual-system integration environment | OSFI regulatory fines up to 3% of global annual revenue under PIPEDA; breach remediation costs benchmarked at CAD 50M–180M depending on scope; customer trust erosion accelerating attrition from newly acquired PC Financial portfolio; class-action liability exposure under Canadian privacy law | Mitigate + Transfer | EQB's concurrent management of two banking environments during migration creates a significantly expanded attack surface across APIs, data pipelines, and access controls. The migration of 3.5M+ customer records including 2M+ credit card accounts and 17.5M PC Optimum loyalty records onto Azure infrastructure creates temporary authentication vulnerabilities that adversaries specifically target during M&A integration windows. Quantified exposure: EMV CAD 68.5M; Monte Carlo mean CAD 57.8M; 95th-percentile tail CAD 200M equivalent to consuming ~50% of EQB's CET1 buffer above OSFI's 10.5% minimum requirement, compounded by the concurrent CAD 105M integration budget and Q4 2025 restructuring charges of CAD 92M (EQB Inc., 2026; OSFI B-13, 2022). | 1. Deploy NIST SP 800-207 zero-trust architecture across all Temenos-Azure migration pipelines: identity-based access controls replacing perimeter-based security; all service-to-service API calls authenticated and encrypted; zero standing privileges during dual-system period (NIST, 2020; OSFI B-13, 2022) 2. Engage a CREST-accredited third-party firm for pre-migration adversarial red-team exercises on the Temenos-Azure integration layer before any PC Financial customer record is transferred (CREST, 2024) 3. Migrate 3.5M records in defined tranches of 500K records per phase; 30-day parallel validation before next tranche begins; maximum blast radius per breach event limited to 500K records (OSFI B-13 phased change management, 2022) 4. Establish dedicated 24/7 Integration Security Operations Centre (SOC) during active migration window; SOC incident count is the primary KRI trigger threshold 5. Enforce AES-256 encryption at rest and TLS 1.3 in transit for all migrated records; mandatory MFA for all privileged access (OSFI B-13, 2022) 6. Transfer residual exposure: negotiate minimum CAD 100M cyber liability policy covering OSFI regulatory fines, PIPEDA class-action defense costs, and first-party breach remediation | CISO / Integration Management Office | Dec 2025 | Open
★R-38 | Strategic / Opportunity | Cross-Sell Conversion Opportunity PC Financial Credit-Card-Only Customers | 9 | 9 | 81 | H | Accelerated deposit and lending growth from conversion of ~2.25M pre-qualified non-deposit cardholders into full EQ Bank customers, driving revenue uplift and EPS accretion above acquisition model | POSITIVE RISK: Faster payback on CAD 800M acquisition cost; primary path to EQB's stated 15%+ ROE target; potential to exceed CAD 30M annual synergy estimate if conversion exceeds 15% within 18 months (EQB Inc., 2025; Defense World, 2026) | Exploit | Approximately 90% of PC Financial's 2.5M credit card holders currently hold no deposit product representing 2.25M pre-qualified, transacting consumers familiar with the PC Financial brand and open to additional products. EQB's exclusive 12-year PC Optimum partnership (17M active members) provides a proprietary, consented marketing channel unavailable to any Big Six competitor. Quantified upside: opportunity EMV +CAD 104M; Monte Carlo mean +CAD 83.6M; optimistic ceiling +CAD 180M. Traditional digital banking customer acquisition cost (CAC): CAD 150–300 per account. PC Optimum-linked conversion CAC: estimated CAD 10–15 per account a 10–20x efficiency advantage (Bain & Company, 2022; EQB Inc., 2025). | 1. Launch structured 90-day post-close cross-sell sprint targeting 2.25M non-deposit cardholders via PC Optimum app notifications (17M members, already-consented channel) and 2,500+ Loblaw in-store kiosk touchpoints (EQB Inc., 2025) 2. Offer 10,000 PC Optimum bonus points (~CAD 10 grocery value) per new EQ Bank HISA or GIC funded within 90 days of migration total incentive cost ~CAD 3.4M to convert 337,500 target accounts, vs. traditional digital CAC of CAD 150–300/account (Bain & Company, 2022) 3. Establish PIPEDA-compliant opt-in consent architecture before campaign launch: explicit consent for financial product marketing using PC Optimum spending data, purpose limitation documentation, Privacy Impact Assessment reviewed and signed off by Chief Privacy Officer (Government of Canada, 2000; CRTC CASL, 2014) 4. Build supervised ML propensity-to-convert model using PC Optimum spending patterns and EQB credit risk indicators; prioritize top two propensity quintiles for initial outreach projected 2× conversion rate improvement vs. untargeted outreach 5. Deploy TDH-EQB Fabric analytics platform to track full conversion funnel from offer impression to funded account; monthly CMO/CDO reporting vs. 15% cumulative conversion target at 18 months | CMO / Chief Digital Officer | Dec 2025 | Open
R-03 | Strategic / Customer | Customer Attrition from PC Financial Portfolio Post-Migration | 7 | 8 | 56 | H | Deposit outflow from the 2.5M migrating customer base; 1% monthly churn = 25,000 customers × CAD 400 LTV = CAD 10M in foregone lifetime value per month | Revenue shortfall reducing EPS accretion below acquisition model; permanent reduction in cross-sell addressable base (each customer lost to attrition is permanently removed from the conversion funnel for ★R-38) | Mitigate | PC Financial customers identify primarily with the Loblaw retail brand, not with EQ Bank. The brand transition and migration process creates a structural vulnerability window during which Canada's Big Six banks and digital challengers Koho (1.2M+ users), Neo Financial, and Revolut Canada are actively targeting this demographic. Financial services M&A research confirms that customers are 3× more likely to remain with an acquired brand when familiar brand signals are maintained during transition (Accenture, 2023). Quantified exposure: EMV CAD 33.0M; Monte Carlo mean CAD 25.8M. Attrition of 5–10% of 2.5M portfolio represents CAD 50M–100M in foregone lifetime value at CAD 400 average LTV (FCAC, 2024). | 1. Retain 'PC Financial, powered by EQ Bank' dual-logo branding for minimum 12 months post-close before advancing to 'EQ Bank (formerly PC Financial)' and full EQ Bank rebrand at 24 months directly leverages the 3× retention benefit from familiar brand signal continuity (Accenture, 2023) 2. Launch co-branded customer communication campaign within 30 days of regulatory approval via PC Optimum notification infrastructure (17M members, zero incremental acquisition cost): exact migration timeline, fee continuity commitments, and CDIC deposit protection status (EQB Inc., 2025) 3. Activate 10,000 PC Optimum bonus points retention incentive (~CAD 10 grocery value) for any PC Financial customer opening an EQ Bank savings or GIC product within 90 days of migration; total cost ~CAD 10/converted customer vs. traditional CAC of CAD 150–300 (Bain & Company, 2022) 4. Pre-build 48-hour activation competitive response playbook for scenarios where Big Six banks or fintechs launch targeted campaigns at transitioning PC Financial customers; trigger: competitor loyalty-linked product launch detected via weekly competitive intelligence monitoring 5. Monitor monthly NPS beginning 30 days pre-migration; NPS decline leads churn acceleration by 30–60 days providing an actionable response window before revenue loss materializes | CMO / Chief Customer Experience Officer | Dec 2025 | Open
R-14 | Regulatory / Data Privacy | PIPEDA / Privacy Compliance Failure Due to Expanded PC Optimum Data Scope | 7 | 8 | 56 | H | OPC regulatory investigation; mandatory breach disclosure; customer privacy complaints across 17.5M PC Optimum loyalty records integrated with EQB banking data | Regulatory fines up to CAD 100,000 per violation under PIPEDA; reputational damage across 17M PC Optimum member base; material disruption to cross-sell strategy if data-sharing is restricted by regulatory order (Government of Canada, 2000) | Mitigate | Integrating PC Optimum transaction data (grocery, pharmacy, fuel spend for 17M Canadians) with EQB banking transaction data creates new consent, purpose limitation, and secondary use obligations under PIPEDA that significantly exceed EQB's prior data processing scope as a savings and mortgage bank. Any secondary use of PC Optimum spending data for financial product marketing without explicit prior consent constitutes a PIPEDA violation. The PC Optimum data asset is simultaneously EQB's primary competitive advantage (★R-38, ★R-40) and its highest data privacy exposure making proactive compliance architecture a prerequisite, not a parallel workstream (Government of Canada, 2000). | 1. Appoint dedicated Privacy Officer for integration with direct reporting to Chief Privacy Officer and Board Risk Committee within 30 days of close 2. Conduct Privacy Impact Assessment (PIA) on all proposed PC Optimum data-sharing use cases before any data is accessed for marketing or analytics; PIA must cover PIPEDA s.5 accountability, s.4.3 consent, and data minimization principles (Government of Canada, 2000) 3. Deploy consent management platform (e.g., OneTrust) for granular opt-in consent for secondary use of PC Optimum spending data in financial product targeting opt-in architecture required; opt-out insufficient under PIPEDA 4. Ensure all cross-sell campaign communications include clear opt-out mechanism compliant with Canada's Anti-Spam Legislation (CASL); legal review of all data-use consents is a prerequisite before any PC Optimum data is accessed for product targeting (CRTC, 2014) 5. All EQB-Loblaw data-sharing agreements reviewed against PIPEDA accountability and openness principles by CPO and external privacy counsel before execution | Chief Privacy Officer / Legal | Dec 2025 | Open
★R-39 | Strategic / Opportunity | Omnichannel Expansion Loblaw Retail Network Opens New Customer Segments | 7 | 8 | 56 | H | Accelerated new customer acquisition across demographic segments not reachable through digital-only banking particularly non-tech-native and senior demographics | POSITIVE RISK: Expanded total addressable market; EQ Bank gains physical presence across 2,500+ national retail locations; increased deposit inflows; enhanced brand awareness beyond digital-first demographics (EQB Inc., 2025) | Exploit | EQB's acquisition of PC Financial provides access to ~2,500 Loblaw store locations, 180+ in-store banking kiosks, and 500+ ATMs transforming EQ Bank from a digital-only institution to an omnichannel bank. Physical kiosk access addresses EQ Bank's known vulnerability: in-person identity verification reduces CNP fraud risk (directly supporting R-17 mitigation) and enables KYC for customers who cannot complete digital-only onboarding. Non-digital customer segments represent a previously inaccessible total addressable market for EQB's savings and GIC products (EQB Inc., 2025). | 1. Activate EQ Bank product account-opening capability at Loblaw in-store kiosks within 60 days of close; each kiosk functions as a zero-marginal-cost digital banking acquisition point with in-person identity verification capability (EQB Inc., 2025) 2. Run structured 2-day Loblaw staff training program on EQ Bank product basics (HISA, GIC, mortgage pre-qualification) within 90 days; provide direct referral portal enabling same-session account opening 3. Negotiate SLAs with Loblaw for kiosk uptime (minimum 98% during banking hours) and ATM network availability within 60 days of close 4. Track new EQ Bank accounts opened via kiosk channel monthly; target 50,000 new accounts within 12 months of close | COO / Chief Digital Officer | Dec 2025 | Open
★R-40 | Strategic / Opportunity | AI Personalization Opportunity PC Optimum Spending Data Enables Targeted Offers | 7 | 8 | 56 | H | Above-forecast revenue from AI-driven personalized cross-sell and upsell; sustainable data-driven competitive advantage that Canada's Big Six cannot replicate at equivalent scale | POSITIVE RISK: Reduced customer acquisition costs; higher lifetime customer value; potential proprietary data moat from PC Optimum transaction-level spending analytics (EQB Inc., 2025) | Exploit | PC Optimum's transaction-level spending data (grocery category, pharmacy, fuel, retail) for 17M Canadians, when combined with EQB banking data, creates a proprietary consumer financial behaviour dataset unavailable to any Big Six competitor. EQB's existing TDH-EQB Fabric near-real-time analytics platform provides the deployment infrastructure. This data asset is the foundation of EQB's personalized product targeting thesis and is the primary driver of the optimistic scenario in the ★R-38 Monte Carlo simulation (+CAD 180M upside). Realizing this opportunity requires PIPEDA compliance as a hard prerequisite (see R-14). | 1. Integrate PC Optimum transaction data with TDH-EQB Fabric within 120 days of close under PIPEDA-compliant opt-in consent framework signed off by Chief Privacy Officer 2. Build supervised ML propensity-to-purchase model: PC Optimum spending patterns and EQB credit risk indicators as features; EQ Bank product adoption as target variable; cross-validated using Leave-One-Out Cross-Validation (LOOCV) on PC Financial pre-migration CRM data to minimize overfitting 3. All model outputs must pass OSFI AI governance review (bias audit, disparate impact testing per Canadian Human Rights Act) and PIPEDA purpose limitation check before deployment (OSFI, 2022) 4. Target top two propensity quintiles for initial campaign outreach; track 2× conversion rate uplift vs. untargeted baseline; monthly CDO performance reporting | Chief Data Officer / Revenue | Dec 2025 | Open
R-17 | Operational / Fraud | Fraud Spike During Integration Account Takeover and CNP Identity Fraud | 9 | 6 | 54 | H | Elevated account takeover fraud and Card-Not-Present (CNP) identity fraud exploiting authentication gaps during the 90-day dual-system integration window | Direct financial losses to customers and EQB; mandatory OSFI and FCAC fraud reporting obligations; reputational damage during brand transition window when customer trust is most fragile. CNP fraud constitutes ~80% of Canadian card fraud losses (Payments Canada, 2024). EMV CAD 25.3M; Monte Carlo mean CAD 20.4M | Mitigate + Transfer | R-17 is operationally distinct from R-01: R-01 concerns external adversarial breach of EQB's systems; R-17 concerns criminal exploitation of customer-facing authentication confusion during the dual-system integration period overlapping customer databases, temporary dual-system access, and inconsistent identity verification protocols. PC Financial's 2M+ active credit card accounts introduce CNP fraud exposure that EQB's current fraud detection models are not calibrated for; EQB's existing models are trained on savings and mortgage product fraud signatures only. Industry data shows CNP fraud incident rates increase 40–60% during financial institution migration windows (Payments Canada, 2024; EMVCo, 2023). | 1. Retrain EQB's fraud detection models on PC Financial's 24-month historical transaction data (CNP velocity patterns, merchant category distributions, geographic anomalies) before migration begins; deploy ensemble model combining EQB's deposit fraud classifier with a new CNP fraud classifier trained on PC Financial data; cross-validate using LOOCV; target ≥90% precision on High-risk transactions 2. Implement step-up MFA for all PC Financial account holders during 90-day dual-system window: triggered by transactions >CAD 1,000, new device login, contact information changes, and cross-system balance transfers (OSFI B-13, 2022) 3. Deploy EMVCo 3-D Secure 2.0 (3DS2) for all online CNP card transactions during migration window with enhanced risk-scoring rules for first-time merchants and geographic anomalies; 3DS2 reduces CNP fraud losses by average 75% vs. static password authentication (Payments Canada, 2024; EMVCo, 2023) 4. Establish dedicated integration fraud surge team within EQB's fraud operations for the 90-day peak window; 24-hour account takeover resolution SLA for escalated PC Financial customer complaints 5. Transfer residual exposure: procure professional indemnity insurance covering fraud remediation costs and mandatory customer reimbursement obligations | CRO / Fraud Prevention Lead | Dec 2025 | Open
R-05 | Operational / HR | Key Talent Loss PC Financial Staff Exit During Transition Uncertainty | 9 | 4 | 36 | M | Loss of institutional knowledge in credit card operations, fraud detection, and compliance; operational gaps requiring expensive contractor backfill at 2–3× FTE cost | Integration delays; elevated HR costs; reduced execution quality in fraud controls (R-17) which depend directly on PC Financial's fraud operations expertise | Mitigate | EQB reduced its workforce 8% in Q4 2025 as part of a restructuring that generated CAD 92M in charges PC Financial staff uncertainty is additive to an already-stressed organizational environment. The loss of credit card operations expertise is particularly consequential because it directly elevates R-17 fraud exposure: PC Financial's fraud team holds the institutional knowledge of the credit card fraud patterns that EQB's models need to be calibrated against. EQB has no prior experience running a credit card portfolio retaining this expertise through the integration window is operationally critical (EQB Inc., 2026). | 1. Identify top 50 critical PC Financial staff (technology, credit card operations, fraud, compliance, and customer experience) within 30 days of close; offer 12-month retention bonus of 15–20% of base salary cliff-vesting at 12 months standard Canadian financial services M&A retention practice benchmarked against Mercer 2023 compensation data (Mercer, 2023) 2. Provide written career pathway documentation within EQB's organizational structure within 60 days; each critical role explicitly mapped to an equivalent EQB position with salary band disclosure 3. All workforce transition actions compliant with Employment Standards Act (Ontario/BC) minimum notice periods and severance requirements per ESA s.54–62 (Government of Canada) 4. Launch joint EQB-PC Financial culture integration sessions within 90 days; monthly employee engagement pulse survey with results to CHRO within 3 days of collection | CHRO / IMO | Dec 2025 | Open
R-06 | Reputational / Brand | Brand Confusion and Reputational Damage During PC Financial Rebrand | 7 | 6 | 42 | M | Customer confusion driving deposit attrition; media scrutiny reducing trust in EQB as deposit-taking institution; long-term dilution of EQ Bank franchise equity in Canadian retail banking | Reputational harm feeding into R-03 attrition acceleration; deposit outflow; potential for media-amplified negative coverage compounding the transition period impact (Accenture, 2023) | Mitigate | PC Financial customers associate their banking relationship with the Loblaw retail brand, not with EQ Bank. An abrupt rebrand during migration removes the primary trust anchor for these customers at the most vulnerable point in the relationship. Financial services M&A research shows customers are 3× more likely to remain with an acquired brand when familiar brand signals are maintained during transition (Accenture, 2023). Brand disruption is the second leading driver of attrition in retail banking M&A, after service disruption (EQB Inc., 2025). | 1. Implement phased 24-month brand transition: Phase 1 (months 0–12) 'PC Financial, powered by EQ Bank'; Phase 2 (months 12–18) 'EQ Bank, formerly PC Financial'; Phase 3 (months 18–24) full EQ Bank rebrand 2. Deploy proactive media strategy 30 days pre-close: structured briefing for Canadian financial media (Globe and Mail, BNN Bloomberg, CBC) anchored to customer benefit continuity and CDIC deposit protection messaging 3. Pre-approve crisis communication playbook with CEO and Board: activation threshold ≥3 major-outlet negative stories within 7 days triggers mandatory 48-hour CMO and CEO response protocol 4. Deploy real-time brand sentiment monitoring across Canadian financial media and social platforms; weekly CMO sentiment dashboard with defined escalation thresholds | CMO / Brand | Dec 2025 | Open
R-07 | Financial / Integration | Integration Cost Overrun Beyond CAD 105M Budget | 7 | 6 | 42 | M | Actual integration spend exceeds projected CAD 105M, compressing near-term EPS and undermining deal economics | EPS dilution below acquisition model; shareholder dissatisfaction; exacerbated by EQB's Q4 2025 restructuring pressure already straining balance sheet capacity (EQB Inc., 2026) | Mitigate | The combined Monte Carlo simulation mean across four threat risks (R-01, R-02, R-03, R-17) is CAD 120.2M already exceeding the disclosed CAD 105M integration budget before any operational overruns are included. This confirms that the integration budget has zero contingency buffer for concurrent risk materialization. EQB's Q4 2025 financial position (revenue down 5% YoY, adjusted net income down 32%, CAD 92M restructuring charges) leaves limited capacity to absorb cost overruns without impacting capital ratios (EQB Inc., 2026). | 1. Establish Integration Management Office (IMO) with monthly budget tracking dashboard; all variances ≥CAD 500K require written CFO approval before proceeding; monthly variance report to Board Risk Committee 2. Build 15% contingency reserve (CAD 15.75M) into the integration budget baseline consistent with PMI contingency reserve best practice for complex IT integrations involving acquired regulated financial entities (PMI, 2021) 3. Identify three pre-approved cost-reduction levers before close: (1) Temenos license consolidation eliminating duplicate PC Financial Temenos licenses estimated at CAD 3–5M/year saving; (2) legacy vendor contract renegotiation; (3) headcount optimization via natural attrition without forced redundancies 4. Quarterly CFO review: if cost-to-synergy ratio exceeds 4:1 at any quarterly milestone, trigger IMO scope review and backup lever activation | CFO / IMO | Dec 2025 | Open
R-08 | Operational / Partnership | Loblaw Co-Dependency Disruption Embedded Operational Partnership Complexity | 5 | 8 | 40 | M | Disruption to in-store banking services at 2,500+ kiosk locations and ATM network; loss of distribution channel during migration; customer access gaps affecting 2.5M transitioning customers | Revenue loss from disrupted service delivery; customer attrition from unavailable in-store banking channel; governance complications from Loblaw's 17% equity stake and two board seats amplifying any commercial dispute | Mitigate | PC Financial's entire physical banking infrastructure 2,500+ kiosk locations, 180+ in-store kiosks, and 500+ ATMs operates through Loblaw's retail estate. Any disruption to this operational relationship during the transition window directly affects EQB's ability to serve the 2.5M migrating customers. Loblaw's 17% equity stake and two board seats create structural alignment but do not contractually protect EQB against operational friction from day-to-day commercial dependencies (EQB Inc., 2025). | 1. Formalize Service Level Agreements (SLAs) with Loblaw for all operational dependencies within 60 days of close: kiosk uptime minimum 98% during banking hours, PC Optimum data feed reliability ≥99.9% uptime, ATM network access continuity 2. Establish joint EQB-Loblaw governance committee co-chaired by EQB COO and Loblaw CFO with monthly operational reviews and formal 30-day arbitration dispute resolution mechanism 3. Include change-of-control provisions in all operational agreements: if Loblaw undergoes ownership change, EQB retains 12-month termination right on all Transition Service Agreements 4. Appoint dedicated EQB Relationship Manager for Loblaw commercial dealings with weekly cadence during first 12 months | COO / CLO | Dec 2025 | Open
R-09 | Strategic / Revenue | Cross-Sell Conversion Failure EQB Fails to Convert PC Financial Customers | 5 | 8 | 40 | M | Below-forecast revenue uplift from the PC Financial customer base; weakened financial justification for the CAD 800M acquisition price if CAD 30M annual synergy target is missed | EPS accretion shortfall below acquisition model; investor disappointment; potential impairment of goodwill recorded on acquisition if conversion rates fall materially below projection | Mitigate | R-09 is the execution failure scenario for the same customer base that drives ★R-38's upside. If the cumulative cross-sell conversion rate falls below 8% at 18 months half of the 15% target the financial rationale for the CAD 800M acquisition price is materially impaired. PC Financial customers have limited prior awareness of EQB's mortgage and savings products; without proactive, data-driven targeting, passive conversion rates are estimated at 3–5% (EQB internal estimate, 2025). | 1. Activate KRI-05 (cumulative conversion rate) monitoring from Day 1 post-close; if Amber threshold triggered (<15% trajectory at 18 months), conduct A/B testing on offer messaging within 30 days and retarget underperforming segments 2. Apply PC Optimum propensity scoring model to prioritize top-quintile outreach projected 2× conversion rate improvement vs. untargeted campaigns; deprioritize lowest quintile to preserve CAC efficiency 3. Track full conversion funnel on TDH-EQB Fabric: offer impression → app download → account application → funded account → 90-day active status; monthly CDO variance reporting against conversion plan | CMO / CDO | Dec 2025 | Open
R-10 | Financial / Market | Interest Rate Sensitivity Mortgage Portfolio Profitability Under Rate Volatility | 5 | 8 | 40 | M | Net interest margin compression on the combined EQB + PC Financial mortgage-heavy portfolio under adverse Bank of Canada rate movements | Lower earnings; impaired deal economics if rate environment compresses margins below the levels assumed in the acquisition revenue model; investor concern over NIM trajectory | Mitigate | The combined EQB + PC Financial balance sheet is disproportionately weighted toward mortgage lending EQB's core product. The Bank of Canada maintained elevated rates through 2024–2025, and any sustained rate decline compresses the fixed-rate mortgage spread that drives EQB's net interest income. The acquisition of PC Financial's credit card receivables adds a higher-yielding but higher-risk asset class that partially offsets this sensitivity, but does not eliminate it (EQB Inc., 2025; OSFI IRRBB Guidelines). | 1. Conduct quarterly Asset-Liability Management (ALM) review of combined balance sheet; maintain Board-approved fixed/variable mortgage ratio to limit NIM exposure to single-direction rate movements 2. Hedge material interest rate exposure using interest rate swaps (IRS) where cost-effective; hedging program consistent with OSFI's interest rate risk in the banking book (IRRBB) guidance 3. Stress-test combined portfolio semi-annually for +200bps and -100bps rate shock scenarios; results reported to Board Risk Committee with NIM sensitivity analysis 4. Leverage EQB's Azure-hosted real-time ALM reporting infrastructure for daily position monitoring (EQB Inc., 2025) | CFO / Treasury | Dec 2025 | Open
R-11 | Regulatory / Capital | Regulatory Capital Requirement Changes OSFI Imposes New Capital Buffers Post-Close | 3 | 8 | 24 | M | Constrained capital available for lending and growth if OSFI imposes additional Pillar 2 capital surcharge on the combined entity following acquisition of a significantly larger deposit base | Strategic flexibility reduction; potential equity raise requirement; pressure on path to 15%+ ROE target if capital ratios are constrained by new OSFI requirements (EQB Inc., 2026) | Mitigate | EQB's current CET1 ratio of 13.3% is 280 basis points above OSFI's 10.5% minimum under Basel III providing a meaningful buffer. However, OSFI may impose additional Pillar 2 capital requirements following the acquisition of a significantly larger and more complex deposit base, including a credit card portfolio that carries higher risk-weight assets than EQB's current product mix. EQB's 2026 target of 12%+ ROE depends materially on avoiding equity-dilutive capital raises (EQB Inc., 2026; OSFI Basel III Implementation Guidelines). | 1. Maintain CET1 ratio minimum 50bps above OSFI regulatory minimum at all times during integration; no dividend payments or share buybacks during integration that would reduce CET1 below 12% 2. Pre-build capital scenario model showing CET1 trajectory under Pillar 2 surcharge scenarios of +50bps, +100bps, and +150bps; present to Board pre-close 3. Brief OSFI proactively within 30 days of close on combined entity capital adequacy trajectory and 24-month deleveraging roadmap (OSFI Basel III Implementation Guidelines) | CFO / Capital Management | Dec 2025 | Open
R-12 | Legal / Vendor | Third-Party Vendor/Contract Disputes Loblaw-Side Service Agreements | 5 | 6 | 30 | M | Service continuity gaps and unexpected vendor renegotiation costs where Loblaw-held service agreements are not assignable to EQB post-close without consent | Operational disruption; elevated vendor costs; potential litigation from contract disputes where assignment consent was not obtained before close | Mitigate | PC Financial operates through Loblaw's vendor ecosystem many service agreements are held by Loblaw on behalf of PC Financial and may include change-of-control clauses that trigger renegotiation rights or automatic termination upon acquisition. Vendor contract complexity is a common and underestimated source of integration cost overruns in financial institution M&A (EQB Inc., 2025). | 1. Audit all PC Financial third-party contracts within 30 days of close: identify change-of-control clauses, assignment restrictions, auto-termination provisions, and contracts with >CAD 1M annual value 2. Obtain written assignment consents from critical vendors before close; legal counsel to review all material contracts (>CAD 1M annual value) within 60 days 3. Prioritize Temenos licensing consolidation to reduce total vendor count and eliminate duplicate SaaS platform fees 4. Renegotiate Loblaw-linked service agreements at independent market pricing within 90 days of close | CLO / Procurement | Dec 2025 | Open
R-13 | Financial / Credit | Credit Quality Deterioration PC Financial Loan Book Higher Default Risk | 5 | 8 | 40 | M | Elevated loan loss provisions and credit card write-offs post-acquisition if PC Financial's credit card book contains undisclosed delinquencies or subprime concentrations | Financial losses reducing deal accretion; OSFI scrutiny; potential requirement for additional capital provisioning if credit losses exceed modeled assumptions in acquisition underwriting | Mitigate | Credit card portfolios structurally carry higher default rates than mortgage portfolios this is expected and priced into the acquisition model. The risk is that PC Financial's specific portfolio contains higher-than-disclosed delinquency rates or geographic/merchant-category concentrations not visible in aggregate due diligence. PC Financial's 2M+ accounts include an unknown proportion of subprime cardholders acquired through Loblaw's retail customer base, which skews toward lower-income demographics (EQB Inc., 2025; OSFI, 2022). | 1. Conduct granular pre-close credit due diligence: analyze all 2M+ credit card accounts by 30/60/90+ day delinquency buckets, credit score distribution, and geographic concentration 2. Stress-test combined loan book for +200bps rate shock and 5% unemployment rate increase, consistent with OSFI supervisory expectations for Schedule I bank acquisitions (OSFI, 2022) 3. Provision adequately at close based on deep-dive findings; provision level reviewed by independent credit review firm retained as a condition of close 4. Negotiate representations and warranties (R&W) insurance covering undisclosed NPLs surfacing within 12 months; 90-day post-close independent credit audit mandatory | CRO / Credit Risk | Dec 2025 | Open
R-15 | Strategic / Competitive | Competitive Poaching of PC Financial Customers by Big Six or Fintechs | 7 | 6 | 42 | M | Customer poaching and market share loss before EQB establishes its value proposition with the transitioning customer base during the 12-month brand migration window | Permanent reduction in cross-sell addressable base (★R-38); weakened competitive position in the everyday banking segment EQB is entering for the first time | Mitigate | Koho reached 1.2M+ users by 2024 by targeting the low-fee digital banking segment that EQB is now entering. Big Six banks particularly TD and RBC have existing credit card plus loyalty program infrastructure and will aggressively pursue the 2.5M transitioning PC Financial customers during the uncertainty window. Every month of brand transition is a month in which competitors have a targeting advantage that EQB's incomplete migration prevents it from neutralizing fully (FCAC, 2024). | 1. Establish weekly competitive intelligence monitoring: track Big Six and Koho/Neo Financial product launches and promotional offers targeting PC Optimum demographics during first 12 months post-close 2. Pre-approve 48-hour rapid-response counter-offer playbook: trigger is competitor loyalty-linked product launch targeting PC Financial transitioning customers; pre-approved response tools include fee waiver offer, PC Optimum bonus acceleration, and dedicated retention call queue 3. Refresh PC Optimum incentive structure quarterly during transition period to maintain competitive differentiation against Big Six loyalty programs (Air Miles, SCENE+) | CMO / Strategy | Dec 2025 | Open
R-18 | Financial / Due Diligence | Inaccurate Due Diligence Hidden Non-Performing Loans Surfacing Post-Close | 3 | 8 | 24 | M | Unexpected credit losses and additional loan loss provisions post-close reducing deal value and EPS below acquisition model | Financial write-downs; investor surprise and credibility risk for management; potential litigation against Loblaw if undisclosed material liabilities are found to have been withheld | Mitigate + Transfer | Time and information constraints in large-scale M&A due diligence create risk that undisclosed non-performing loans or contingent liabilities escape detection, particularly in PC Financial's CAD 5.8B asset base which includes credit card receivables a more opaque asset class than EQB's primarily mortgage-backed book. Post-close surprises in the loan book would also damage EQB's credibility with OSFI and investors at a critical integration period (EQB Inc., 2025; CRO, EQB). | 1. Conduct enhanced credit quality review of PC Financial's full loan book as a condition precedent to close: 30/60/90+ day delinquency analysis by product type, geographic concentration, and merchant category default rate analysis on credit card receivables 2. Engage independent credit review firm to validate PC Financial's provisioning adequacy; firm's findings to be shared with OSFI as part of the regulatory approval package 3. Transfer: Require representations and warranties (R&W) insurance covering undisclosed NPLs and hidden liabilities surfacing within 12 months of close 4. Conduct mandatory 90-day post-close independent credit audit with results to EQB Board within 120 days | CRO / M&A Advisory | Dec 2025 | Open
R-19 | Operational / HR | HR Integration Friction Misaligned Compensation, Benefits, and Organizational Culture | 7 | 4 | 28 | M | Employee dissatisfaction, grievances, and operational friction delaying normalization across the combined workforce of approximately 1,500+ staff | Elevated HR costs from grievances and remediation; morale decline; productivity reduction in integration workstreams; attrition of experienced staff during the critical first 90 days | Mitigate | EQB absorbed an 8% workforce reduction in Q4 2025 generating CAD 92M in restructuring charges the cultural fatigue and change management load within EQB is already elevated before PC Financial staff integration begins. Compensation structures, benefits packages, and cultural norms differ materially between a Toronto-based digital challenger bank and a Loblaw-embedded retail financial services operation (EQB Inc., 2026; Government of Canada, Employment Standards Act). | 1. Conduct HR compensation parity analysis pre-close: compare all PC Financial salary bands to EQB equivalents by role level; identify compensation gaps exceeding 10% requiring harmonization within 90 days 2. All workforce transition actions compliant with Employment Standards Act (Ontario/BC) minimum notice periods and severance per ESA s.54–62 (Government of Canada); no role eliminations without prior legal counsel review 3. Launch joint culture integration sessions within 90 days with structured EQB buddy-system pairing for PC Financial staff and shared integration goals 4. Monthly employee engagement pulse survey (5 questions, results to CHRO within 3 days); escalate to CEO if engagement score declines >15% vs. baseline or voluntary turnover exceeds 8% annualized in any 30-day period | CHRO | Dec 2025 | Open
R-20 | Financial / Liquidity | Liquidity Risk Unexpected Deposit Withdrawal Surge Post-Migration | 3 | 8 | 24 | M | Liquidity pressure requiring emergency funding or asset sales if PC Financial customer confidence wavers and deposits exit the combined entity faster than modeled | OSFI regulatory intervention under Liquidity Coverage Ratio (LCR) monitoring; reputational damage if funding gaps emerge during integration; cascading impact on R-03 attrition acceleration | Mitigate | PC Financial customers may withdraw deposits during brand transition uncertainty R-20 is operationally linked to R-03 attrition risk. A 5% withdrawal rate from the combined CAD 5.8B PC Financial asset base represents a CAD 290M liquidity event. EQB's current HQLA buffer must be explicitly sized to absorb this scenario without breaching OSFI's LCR minimum of 100% (EQB Inc., 2025; OSFI LCR Guidelines). | 1. Maintain HQLA buffer above OSFI's 100% LCR minimum at all times during integration no exceptions permitted during first 90 days post-migration 2. Monitor daily deposit runoff KPI from Day 1 post-migration; OSFI LCR stress reporting triggered if daily runoff exceeds 2% of total migrated PC Financial deposit base 3. Prepare Board-approved contingency funding plan pre-close identifying secondary liquidity sources (CMHC mortgage bond program, CDIC-eligible covered bonds) activated if deposit runoff exceeds 5% in any 7-day window (OSFI LCR Guidelines; EQB Inc., 2025) | Treasurer / CRO | Dec 2025 | Open
R-21 | Operational / Partnership | Loblaw Relationship Deterioration Commercial Dependencies Create Ongoing Friction | 5 | 6 | 30 | M | Stalled Transition Service Agreements (TSAs), unresolved commercial disputes, and operational dependencies persisting beyond planned timelines | Integration delays; elevated transition service costs; governance complications from Loblaw's 17% equity stake and two board seats creating conflicts of interest if commercial relationship deteriorates | Mitigate | Loblaw holds 17% EQB equity and two board seats structural alignment reduces but does not eliminate partnership friction. Post-close commercial dependencies (kiosk operations, PC Optimum data feeds, ATM network, IT transition services) create ongoing negotiation points that become contentious when interests diverge. The 12-year PC Optimum exclusivity agreement provides strategic protection but does not address day-to-day operational friction from TSA dependencies that may persist 18–24 months post-close (EQB Inc., 2025). | 1. Negotiate detailed Transition Service Agreements with Loblaw pre-close covering all operational dependencies; set firm TSA expiry dates (maximum 24 months for all service agreements) 2. Establish joint EQB-Loblaw steering committee co-chaired by EQB CEO and Loblaw CFO with monthly operational reviews; 30-day formal arbitration clause for unresolved commercial disputes 3. Assign dedicated EQB Relationship Manager for Loblaw commercial dealings with weekly touchpoint cadence during first 12 months post-close | CEO / CLO | Dec 2025 | Open
R-02 | Regulatory / Compliance | Regulatory Approval Delay OSFI / Minister of Finance Review Extended | 3 | 8 | 24 | M | Delayed deal close beyond calendar 2026 target; prolonged operational limbo extending staff and customer uncertainty; each additional quarter without approval costs ~CAD 7.5M in foregone synergies against the CAD 105M integration budget | Potential deal renegotiation or termination if delay exceeds 18 months; permanent impairment of cross-sell thesis if conditional approval restricts PC Optimum data use estimated CAD 60M+ in foregone 3-year synergies (EQB Inc., 2025; Competition Bureau Canada, 2024) | Mitigate | The deal requires approval from Canada's Minister of Finance under the Bank Act and clearance from the Competition Bureau under the Competition Act. Applications were filed with OSFI and the Competition Bureau in January 2026. Loblaw's 17% equity stake and two board seats, combined with the concentration of financial and loyalty data under a single challenger bank, are the primary regulatory scrutiny triggers. Historical range for Canadian Bank Act Schedule I acquisition approvals: 90–270 days. A conditional approval restricting PC Optimum data use would permanently impair EQB's AI personalization and cross-sell strategy the primary financial rationale for the CAD 800M acquisition price (Competition Bureau Canada, 2024; EQB Inc., 2025). | 1. Submit comprehensive Bank Act Schedule I acquisition application with dedicated data-governance annex addressing PC Optimum data concentration concerns the primary Competition Bureau scrutiny trigger; include Privacy Impact Assessment and ring-fenced data use framework (Competition Bureau Canada, 2024) 2. Prepare three integration contingency budgets: 6-month delay (~CAD 15M additional carrying cost), 9-month delay (~CAD 22.5M), and 12-month delay (~CAD 30M = one full year of synergy foregone) 3. Retain Canadian M&A regulatory counsel with Schedule I bank approval experience; 10-business-day SLA for all Supplemental Information Request (SIR) responses 4. Establish bi-weekly Board regulatory status updates from filing date; any SIR received triggers an emergency Board session within 5 business days | CLO / CRO | Dec 2025 | Open
R-23 | Reputational / Media | Adverse Media Coverage Amplifying Customer Churn During Integration | 5 | 6 | 30 | M | Negative press coverage accelerating customer attrition and reducing investor confidence during the integration period | Brand damage amplifying R-03 churn velocity; share price pressure; potential OSFI inquiries triggered by media reports of operational incidents (EQB Inc., 2025) | Mitigate | EQB's acquisition of PC Financial is one of the highest-profile Canadian financial services transactions of 2025–2026. Any integration incident service outage, fraud spike, data error will attract disproportionate Canadian financial media attention. Brand disruption amplified by media is a leading accelerant of customer churn in retail banking M&A transitions (Accenture, 2023). A single high-profile incident during the migration window could trigger a media cycle that overwhelms EQB's retention campaign efforts. | 1. Retain a Canadian PR firm with financial services crisis communication experience on retainer for the full integration period (~CAD 300K/year); crisis playbook activation threshold: ≥3 major-outlet negative stories within any 7-day period 2. Pre-approve CEO/CMO media response protocols: 24-hour response SLA for Tier 1 incidents (data breach, significant outage); 48-hour SLA for Tier 2 incidents (isolated service disruption) 3. Deploy 24/7 brand sentiment monitoring across Canadian financial media and social platforms; weekly CMO sentiment report with defined escalation thresholds | CCO / Investor Relations | Dec 2025 | Open
R-26 | Financial / Synergy | Failure to Achieve CAD 30M Annual Cost Synergy Targets | 7 | 6 | 42 | M | Lower-than-projected EPS accretion; revised investor guidance required if synergy delivery timeline slips materially | Investor confidence erosion; share price pressure; management credibility risk; delayed return to EQB's stated 15%+ ROE target (EQB Inc., 2026; Defense World, 2026) | Mitigate | The Monte Carlo simulation mean across four threat risks (CAD 120.2M) already exceeds the CAD 105M integration budget if concurrent with synergy underperformance, deal economics deteriorate materially. EQB's Q4 2025 results (adjusted net income down 32% YoY) mean there is limited financial cushion to absorb both integration cost overruns and synergy shortfalls simultaneously without impacting capital ratios and investor confidence (EQB Inc., 2026). | 1. Build synergy tracking dashboard with monthly CFO reporting against CAD 30M annual target; identify specific synergy levers pre-close: (1) Temenos license consolidation estimated CAD 3–5M/year; (2) legacy vendor contract renegotiation; (3) headcount optimization via natural attrition without forced redundancies 2. Tie 10–20% of annual variable compensation for CFO, COO, and IMO leads to synergy delivery milestones at Month 12 and Month 24 3. Quarterly Board review with variance analysis: if synergy realization tracking below 70% of target at Month 6, trigger IMO scope review and backup lever activation | CFO / Strategy | Dec 2025 | Open
R-27 | Regulatory / AML | AML Compliance Gaps PC Financial Anti-Money Laundering Controls | 3 | 8 | 24 | M | AML violations, FINTRAC enforcement actions, and mandatory remediation programs if PC Financial's transaction monitoring does not meet FINTRAC Guideline B-8 standards | Regulatory fines from FINTRAC; reputational damage; mandatory supervised remediation program disrupting integration operations (FINTRAC, 2022) | Mitigate | PC Financial's credit card CNP channel is a structurally higher-risk AML vector than EQB's deposit-focused business CNP transactions are harder to attribute to specific customers and are more frequently used in trade-based money laundering typologies. EQB's existing AML controls are designed for savings and mortgage products and are not calibrated for credit card CNP monitoring. FINTRAC Guideline B-8 compliance for the combined entity's full product set must be established within 90 days of close (FINTRAC, 2022). | 1. Conduct AML controls gap assessment of PC Financial's transaction monitoring and Suspicious Transaction Report (STR) infrastructure against FINTRAC Guideline B-8 standards within 60 days of close (FINTRAC, 2022) 2. Identify and remediate gaps in PC Financial's CNP channel transaction monitoring specifically address CNP-specific AML typologies not covered by EQB's existing deposit-focused monitoring rules 3. File updated AML compliance program documentation with FINTRAC within 90 days of close as required for acquiring entities under FINTRAC guidance 4. Retrain PC Financial staff on EQB's AML policies and FINTRAC reporting obligations within 60 days of close | CCO / AML Officer | Dec 2025 | Open
R-28 | Operational / Change Mgmt | Change Management Fatigue Integration Workload Overwhelming Internal Teams | 7 | 4 | 28 | M | Missed integration milestones, quality degradation in critical workstreams, and employee burnout across EQB's post-restructuring workforce | Integration delays; elevated error rates in critical data migration and compliance workstreams; talent attrition among EQB's own high performers during the execution window when they are most needed | Mitigate | EQB's Q4 2025 restructuring 8% workforce reduction, CAD 92M in charges means the integration workload falls on a smaller, more stressed organizational base. PC Financial's integration is the largest operational undertaking in EQB's history, and it is being executed concurrently with the post-restructuring stabilization period. Change management fatigue in mid-market bank M&A integrations is a primary driver of integration cost overruns and milestone delays (PMI, 2021; EQB Inc., 2026). | 1. Establish dedicated IMO with minimum 3 FTE integration Project Managers; integration workstream participants capped at 40% of working hours 60% protected for BAU operations; no concurrent workstream launches without IMO sign-off 2. Conduct monthly employee engagement pulse survey (5 questions, results to CHRO within 3 days); escalate to CEO if engagement score declines >15% vs. baseline or voluntary turnover exceeds 8% annualized in any 30-day period 3. Implement milestone governance: each integration workstream has defined go/no-go gates; no new workstreams launched without IMO approval (PMI Change Management Guidelines, 2021) | CHRO / IMO | Dec 2025 | Open
R-30 | Operational / Technology | Underestimating IT Infrastructure Age Legacy PC Financial Systems | 5 | 6 | 30 | M | Higher-than-budgeted technology remediation costs and longer integration timelines if PC Financial's non-Temenos legacy systems require more extensive modernization than disclosed in due diligence | Cost overruns compressing the CAD 105M integration budget; delayed synergy realization; operational risk from running aging systems beyond planned decommission dates | Mitigate | While both organizations share the Temenos core banking platform, PC Financial's ancillary systems middleware, data warehouses, ATM management software, and API gateway infrastructure are configured independently and have not been assessed for Azure compatibility or migration complexity. Configuration divergence, not platform incompatibility, is the primary technology integration risk. Underestimation of legacy system age is one of the top three sources of M&A integration budget overruns in financial services (EQB Inc., 2025). | 1. Commission independent technical due diligence on all PC Financial non-Temenos systems within 30 days of close: middleware, data warehouses, ATM management software, legacy reporting systems 2. Allocate dedicated IT remediation contingency budget of 15% of the CAD 105M integration budget (= CAD 15.75M) with CFO-approved release triggers and monthly spend tracking 3. Develop phased IT modernization roadmap: Priority 1 (0–6 months) systems touching customer data; Priority 2 (6–12 months) operational systems; Priority 3 (12–24 months) reporting and analytics infrastructure | CTO / IMO | Dec 2025 | Open
R-31 | Strategic / Partnership | Loss of PC Optimum Co-Branding Benefits Due to Loyalty Program Restructuring | 7 | 6 | 42 | M | Customer dissatisfaction and attrition acceleration if PC Optimum-linked banking benefits are reduced or removed following any Loblaw restructuring of the loyalty program | Accelerated R-03 customer churn; direct impairment of ★R-38 cross-sell thesis if PC Optimum points incentive structure is weakened by Loblaw unilaterally; loss of the primary competitive differentiator that justified the CAD 800M acquisition price | Mitigate | The 12-year PC Optimum exclusive financial services partnership is the cornerstone of EQB's entire acquisition thesis it underpins the cross-sell strategy (★R-38), the AI personalization capability (★R-40), and EQB's competitive differentiation against the Big Six. Any Loblaw restructuring of the PC Optimum program (reduction in member base, changes to points redemption economics, or elimination of financial product exclusivity) would directly impair the financial rationale for the CAD 800M acquisition price (EQB Inc., 2025; CLO, EQB). | 1. Ensure the 12-year PC Optimum exclusivity agreement includes enforceable: (1) change-of-control protections if Loblaw is acquired; (2) explicit exclusivity scope covering savings, GIC, credit card, and mortgage product referrals; (3) minimum annual PC Optimum point issuance commitments tied to EQB product adoption milestones; (4) remedies if Loblaw reduces PC Optimum active member base below 15M 2. Develop EQB-native loyalty capability in parallel (18-month horizon) as a structural hedge against PC Optimum program dependency 3. Quarterly PC Optimum partnership health review co-attended by EQB CMO and Loblaw PC Optimum program lead; any proposed program changes require 90-day advance notice per commercial agreement | CLO / CFO | Dec 2025 | Open
R-32 | Financial / Macro | Geopolitical / Macro Shock Recession or Canadian Housing Market Correction | 3 | 9 | 27 | M | Elevated mortgage defaults, increased loan loss provisions, and reduced portfolio valuations across EQB's mortgage-heavy combined balance sheet under a severe macro scenario | Material financial losses reducing capital ratios; OSFI-mandated additional provisioning; potential impairment of acquisition economics if housing correction coincides with the integration period when EQB's financial buffer is already compressed by CAD 105M integration costs | Mitigate | EQB's combined balance sheet with PC Financial is disproportionately weighted toward residential mortgage lending in major Canadian markets. A housing correction of 10% or greater which the Bank of Canada and CMHC have identified as a plausible tail scenario under sustained elevated interest rates would disproportionately affect EQB's NIM and capital adequacy. EQB's CET1 of 13.3% provides ~CAD 400M buffer above OSFI's 10.5% minimum, but this buffer is being consumed concurrently by the CAD 105M integration budget (EQB Inc., 2026; OSFI Stress Testing Guidelines, 2023). | 1. Conduct annual stress test of combined EQB + PC Financial balance sheet against: (1) +300bps rate increase scenario; (2) 10% residential property value decline; (3) 2% unemployment rate increase consistent with OSFI supervisory stress test expectations for Schedule I banks (OSFI Stress Testing Guidelines, 2023) 2. Maintain CET1 buffer ≥50bps above OSFI minimum at all times during integration; no dividend payments or share buybacks that would reduce CET1 below 12% until integration is substantially complete 3. Diversify geographic mortgage concentration: target maximum 40% single-market exposure in any CMHC region within 24 months of close | CFO / CRO | Dec 2025 | Open
R-37 | Financial / Capital Markets | EQB Credit Rating Downgrade Due to Acquisition Leverage | 3 | 8 | 24 | M | Higher borrowing costs and reduced capital market access if DBRS Morningstar or S&P Global downgrade EQB's credit rating following acquisition leverage | Increased funding costs for GIC and mortgage products that are EQB's core revenue drivers; potential covenant breaches on existing debt; share price pressure from rating action headline risk (DBRS Morningstar, 2025; EQB Inc., 2026) | Mitigate | EQB's Q4 2025 balance sheet already shows stress revenue down 5% YoY, adjusted net income down 32%, CAD 92M restructuring charges. The incremental financial leverage from the CAD 800M acquisition may prompt DBRS Morningstar and S&P Global (EQB's primary rating agencies) to review their ratings. A downgrade directly increases EQB's cost of funding for the GIC deposits and mortgage products that generate its core net interest income potentially compressing the margins that the acquisition is designed to improve (EQB Inc., 2026; DBRS Morningstar, 2025). | 1. Maintain leverage ratios within parameters communicated to DBRS Morningstar and S&P Global in pre-deal rating agency briefings; no actions that breach communicated leverage constraints without prior agency consultation 2. Schedule proactive rating agency briefings within 30 days of close: present integration plan, synergy timeline, and CET1 path to pre-acquisition levels within 24 months 3. Model CET1 trajectory under base, stress, and downside scenarios; share deleveraging roadmap with rating agencies to demonstrate capital adequacy sustainability | CFO | Dec 2025 | Open
R-04 | Operational / Data | Data Migration Failure or Corruption of 3.5M Customer Records | 3 | 9 | 27 | M | Data loss, transaction errors, service outages, and regulatory scrutiny over data integrity during transfer of 3.5M+ customer records to EQB's Temenos platform | Operational disruption requiring emergency rollback; mandatory PIPEDA breach reporting if personal information is compromised during migration; OSFI sanctions for data integrity failure; customer harm and associated reputational damage | Mitigate | PC Financial's 3.5M customer records, including credit card transaction histories, identity data, and PC Optimum linkage data, must be migrated to EQB's Temenos configuration from PC Financial's separate Temenos instance. While the shared platform reduces the risk of structural incompatibility, configuration divergence between EQB's and PC Financial's Azure tenants different access control schemas, API architectures, and data lake environments creates meaningful risk of data corruption during the transformation and loading process. I=9 reflects the catastrophic downstream impact: corrupted customer records can trigger PIPEDA mandatory disclosure obligations affecting 3.5M individuals (EQB Inc., 2025; OSFI B-13, 2022; Government of Canada, 2000). | 1. Full encrypted backup of PC Financial customer database stored in a geographically separate Azure region before each 500K-record migration tranche begins (OSFI B-13, 2022) 2. 30-day parallel validation: both legacy PC Financial Temenos instance and EQB Temenos instance process transactions simultaneously; automated reconciliation checks on record counts, account balances, and transaction histories before next tranche proceeds 3. Maintain documented rollback plan with maximum 4-hour Recovery Time Objective (RTO) per tranche; rollback decision authority: CTO in consultation with IMO lead 4. All migration scripts version-controlled in the EQB-Group2 GitHub repository; no manual interventions on production data without dual-sign-off from CTO and CISO | CTO / CISO | Dec 2025 | Open
R-16 | Operational / Technology | Operational Downtime During System Cutover | 3 | 6 | 18 | L | Customers temporarily unable to access accounts, make payments, or use credit card services during planned cutover windows | Customer frustration; FCAC complaint risk if outage extends beyond communicated window; reputational damage if cutover is perceived as unplanned | Accept | Likelihood is low given the shared Temenos platform which significantly reduces cutover complexity compared to dual-platform migrations. Planned maintenance outages are a standard, FCAC-accepted feature of banking system upgrades when properly communicated to customers in advance. The risk is accepted at current score; contingency measures are in place to contain impact within acceptable service levels. | Contingency measures (no active mitigation spend required): 1. Schedule all cutovers during lowest-traffic windows (Saturday 02:00–05:00 ET, validated against EQB transactional volume data) 2. Pre-notify all PC Financial customers 14 calendar days in advance via PC Optimum app and email; communicate exact service interruption window and affected services 3. Test rollback procedures on staging environment before each tranche; enforce maximum 4-hour service restoration window Escalation trigger: Escalate to active mitigation if any unplanned outage exceeds 4 hours or FCAC complaint volume exceeds 50 per cutover event | CTO / IMO | Dec 2025 | Open
R-22 | Legal / HR | Legal Challenges from PC Financial Employees Wrongful Dismissal Claims | 3 | 6 | 18 | L | Litigation costs and management distraction from wrongful dismissal or employment class action claims during workforce integration | Financial liability; reputational harm; operational distraction from a time-critical integration execution period | Accept | Likelihood is low given EQB's planned Employment Standards Act compliance and the active retention program in place under R-05 mitigation. Employment law counsel is retained as standard practice in any M&A transaction. The risk is accepted at current score; standard legal protocols and HR governance are sufficient controls without dedicated mitigation spend. | Contingency measures: 1. Document all workforce transition decisions with written rationale; no role eliminations without prior legal counsel review and ESA compliance confirmation 2. Employment law counsel on retainer with 48-hour response SLA for any escalated employee matters Escalation trigger: Escalate to active mitigation if a formal Ontario Labour Relations Board (OLRB) complaint is filed or class action notice is received | CHRO / CLO | Dec 2025 | Open
R-24 | Legal / Compliance | Mis-Selling or Product Suitability Complaints from PC Financial Customers | 3 | 6 | 18 | L | Regulatory complaints to FCAC and reputational damage from product suitability failures during cross-sell campaigns | Regulatory fines; customer remediation costs; potential FCAC public enforcement action if suitability failures are systemic | Accept | Likelihood is low given EQB's existing FCAC-compliant product suitability framework which will apply to all migrated PC Financial customers. EQ Bank has maintained a strong consumer protection track record recognized on the Forbes World's Best Banks list annually since 2021. The risk is accepted at current score with standard compliance monitoring protocols. | Contingency measures: 1. Train all EQB frontline staff on PC Financial product suitability standards within 90 days of close 2. Deploy complaints monitoring dashboard with 30-day resolution SLA for FCAC-escalated complaints Escalation trigger: Escalate to active mitigation if FCAC complaint volume from migrated PC Financial customers exceeds 1.5× EQB's pre-acquisition monthly complaint baseline in any single month (FCAC, 2024) | CCO / CMO | Dec 2025 | Open
R-25 | Operational / Technology | Technology Vendor Lock-In EQB Inherits Legacy PC Financial Contracts | 5 | 4 | 20 | L | Constrained technology modernization options and elevated vendor costs from inherited PC Financial contracts with high exit penalties or unfavorable terms | Higher-than-projected ongoing IT costs; strategic inflexibility in technology roadmap evolution post-integration | Accept | Likelihood of material impact is low given the shared Temenos platform the primary technology infrastructure is already consolidated. Ancillary vendor contracts represent manageable exposure that standard due diligence and contract management practices can address without dedicated mitigation investment. The risk is accepted at current score. | Contingency measures: 1. Inventory all PC Financial vendor contracts within 60 days of close; identify exit clauses, expiry dates, and any contracts with remaining terms >24 months and no exit provision 2. Prioritize Temenos license consolidation to reduce total vendor count Escalation trigger: Escalate to active mitigation if a vendor contract with no exit clause, >CAD 2M annual value, and remaining term >24 months is identified post-close | CTO / Procurement | Dec 2025 | Open
R-29 | Reputational / ESG | ESG Reputational Risk Association with Loblaw ESG Controversies | 5 | 4 | 20 | L | Reputational damage by association and institutional investor ESG rating pressure if Loblaw faces a material ESG controversy during the EQB integration period | ESG rating downgrades for EQB; institutional investor concern; reputational harm from perceived association with Loblaw corporate controversies | Accept | Impact is moderate-low given EQB operates as an independent federally regulated bank with a separate public profile. Loblaw's ESG risk profile is well-documented and known to investors entering the transaction. EQB's association risk is further limited by Loblaw's role as a commercial partner, not a parent company. The risk is accepted at current score with standard monitoring and communications protocols. | Contingency measures: 1. Quarterly EQB ESG positioning review; pre-approved CEO statement template for material Loblaw ESG events, positioning EQB as independent financial services partner Escalation trigger: Escalate to active mitigation if Loblaw faces a material regulatory enforcement action (Competition Bureau pricing investigation, CRTC enforcement) that generates sustained national media coverage directly implicating the EQB commercial partnership | CEO / Comms | Dec 2025 | Open
R-33 | Legal / Financial | Insurance and Indemnity Gaps Representations and Warranties Coverage Insufficient | 3 | 6 | 18 | L | EQB bears uninsured financial exposure for undisclosed liabilities surfacing post-close beyond the R&W insurance policy limits | Unexpected financial losses; potential litigation against Loblaw for undisclosed material liabilities; impaired deal economics if uncovered liabilities are material | Accept | Likelihood is low given that R&W insurance is being procured as a standard component of the transaction, and its adequacy is addressed as a condition of close under R-18 mitigation actions. The R&W insurance market for Canadian Schedule I bank acquisitions is well-developed, with standard coverage for disclosed risk categories. The risk is accepted at current score. | Contingency measures: 1. CLO reviews R&W policy limits against all material risk categories identified in due diligence within 30 days of policy issuance; escrow arrangement to cover any high-risk uncovered liability categories Escalation trigger: Escalate to active mitigation if post-close audit (R-18 action) identifies a material liability category >CAD 5M not covered by the R&W policy | CLO / CFO | Dec 2025 | Open
R-34 | Governance | Governance Integration Lag PC Financial Board and Committee Structures | 3 | 4 | 12 | L | Governance confusion and delayed decision-making authority if PC Financial board and committee structures are not dissolved cleanly post-close | Corporate governance failure; potential regulatory concern from OSFI; integration delays from conflicting board-level direction during the transitional period | Accept | Governance wind-down of an acquired entity is a standard post-close administrative process that EQB's existing legal and governance team can manage without dedicated resources. EQB's governance framework is well-established; Loblaw's two board seats provide strategic continuity during the transition. This is the lowest-scoring risk in the register and requires no active mitigation investment. | Contingency measures: 1. Appoint EQB Board integration committee within 30 days of close; complete full governance integration (PC Financial board dissolution, committee restructuring) within 90 days Escalation trigger: Escalate if PC Financial governance structures remain unresolved beyond 90 days and create documented decision-making conflicts or OSFI governance concerns | Board / General Counsel | Dec 2025 | Open
R-35 | Operational / AI-Data | AI-Driven Personalization Biased or Discriminatory Model Outcomes | 3 | 6 | 18 | L | Discriminatory lending or product targeting outcomes affecting protected groups under the Canadian Human Rights Act if AI models embed bias from PC Optimum spending data | Regulatory sanctions from FCAC or OSFI; reputational damage; potential class-action liability for discriminatory product targeting | Accept | Likelihood is low given EQB's existing AI governance practices and the planned pre-deployment bias auditing protocol. OSFI has issued guidance on responsible AI use in financial services and EQB's compliance framework already covers model governance. Bias risk is manageable through standard pre-deployment testing without requiring dedicated mitigation spend beyond the existing AI governance program (OSFI, 2022). | Contingency measures: 1. Pre-deployment bias audit for all personalization models using PC Optimum data: demographic fairness testing across age, geography, and income proxy variables; human-in-the-loop review for AI-driven credit decisions (OSFI AI Guidance; Canadian Human Rights Act) Escalation trigger: Escalate to active mitigation if pre-deployment audit identifies disparate impact exceeding 20% across any protected demographic group | CDO / CCO | Dec 2025 | Open
R-36 | Operational / Technology | TDH-EQB Fabric Analytics Platform Fails to Scale to 3.5M Customers | 3 | 6 | 18 | L | Analytics and personalization capabilities degrade under 3.5M customer data volume, reducing cross-sell targeting effectiveness | Reduced AI-driven revenue contribution from ★R-38 and ★R-40; delayed cross-sell strategy execution; elevated re-engineering costs for platform remediation | Accept | Likelihood is low given TDH-EQB Fabric is deployed on Microsoft Azure with elastic auto-scaling, and Azure's compute capacity is not a binding constraint at 3.5M customer data volumes. EQB's existing cloud architecture has been built and tested at scale, and the platform migration from ~600K to 3.5M users represents a 6× volume increase well within Azure's elastic scaling parameters. | Contingency measures: 1. Conduct load testing at 5× current customer volume before migration begins; validate Azure auto-scaling rules are correctly configured for peak load scenarios 2. Engage Microsoft Fabric specialists for pre-migration architecture review if load testing reveals >20% performance degradation at 2× current volume Escalation trigger: Escalate to active mitigation if load testing at 2× current volume reveals >20% degradation in query response times on the TDH-EQB Fabric platform | CTO / CDO | Dec 2025 | Open

## Legend
RT&RP Column Reference Guide
Column | Description
Risk ID | Unique risk identifier. ★ prefix = Positive Risk (opportunity)
Category | Risk domain classification [Operational/Cyber, Financial/Credit, Strategic/Opportunity
Risk Description | Concise risk statement
L (Likelihood) | Probability scale: 1=Very Unlikely, 3=Somewhat Unlikely, 5=50-50, 7=Somewhat Likely, 9=Very Likely
I (Impact) | Impact scale: 1=Very Low, 2=Somewhat Low, 4=Moderate, 6=Somewhat High, 8=High, 9=Extremely High
Score | Risk Score = Likelihood × Impact (range 1–81)
Priority | H = High (≥45) ¦ M = Medium (21–44) ¦ L = Low (≤20)
Resulting In | Immediate/direct consequence if risk materializes
Consequence / Impact | Financial, regulatory, and reputational impact
Response Strategy | MITIGATE: Reduce risk via actionable controls and processes TRANSFER: Move financial exposure to third party (insurance, indemnity) EXPLOIT: Maximize realization of positive risk/opportunity ACCEPT: Monitor at current score; activate contingency if risk escalates
Justification | Business rationale for selected response strategy, grounded in quantitative exposure data and organizational context
Response Actions | Specific, sequenced actions with timelines, accountabilities, and data/regulatory references
Risk Owner | Executive accountable for monitoring and response activation
Date Identified | Date risk was formally registered in the risk register
Status | Open / In Progress / Closed / Accepted