# 5. Risk Response Strategy

The risk response strategy for EQB's acquisition of PC Financial is designed to operationalize the insights derived from the preceding qualitative assessment, I&W analysis, Random Forest classification, and Monte Carlo simulation. The strategy is structured around five priority risks — R-01 Cybersecurity Breach, R-02 Regulatory Approval Delay, R-03 Customer Attrition, R-17 Fraud Spike, and R-38 Cross-Sell Conversion Opportunity — and follows the standard four-category risk response taxonomy: Avoid, Transfer, Mitigate (Reduce), and accept. Each response strategy is calibrated to the risk's quantified Expected Monetary Value (EMV), Monte Carlo simulation mean, and the I&W warning thresholds established in the quantitative assessment.

The net threat contingency reserve recommended by the Monte Carlo simulation is CAD 120.2 million (combined across R-01, R-02, R-03, and R-17). This figure serves as the financial floor for EQB's integration risk budget. The risk responses below are sequenced to prioritize actions that most efficiently reduce this exposure, while also maximizing the probability of realizing R-38's CAD +83.6 million opportunity upside.

## 5.1 R-01: Cybersecurity Breach During IT Integration (EMV: CAD 68.5M)

Response Category: Mitigate (Primary) + Transfer (Secondary)

Given the catastrophic potential impact of a cybersecurity breach — estimated at up to CAD 200M in the pessimistic Monte Carlo scenario — avoidance is not feasible (integration is essential to the deal thesis), and pure acceptance is inappropriate given OSFI B-13 mandatory obligations. The primary response is an aggressive mitigation strategy executed through EQB's Integration Management Office (IMO), with risk transfer through cyber insurance as a secondary layer.

Mitigation Actions:

- Zero-Trust Architecture Deployment: Implement identity-based access controls across all migration pipelines, replacing the legacy perimeter-based security model used during the dual-system integration period. All service-to-service communication must be authenticated and encrypted.

- Pre-Migration Penetration Testing: Engage a CREST-certified third-party security firm to conduct red team exercises on the Temenos-Azure integration layer before any PC Financial customer data is transferred.

- Security Operations Centre (SOC) Escalation: Establish a dedicated integration SOC staffed 24/7 during the active migration window. Alert thresholds aligned to I&W indicators: ≥5 high/critical security incidents per month triggers Red protocol and executive notification.

- OSFI B-13 Compliance Protocol: Appoint a dedicated regulatory liaison for breach notification. Maintain pre-drafted incident response communications for OSFI, affected customers, and public disclosure within the 72-hour mandatory notification window.

- Data Migration Phasing: Migrate PC Financial customer records in tranches rather than in a single cutover, reducing the exposure window and limiting the blast radius of any single point of failure.

Transfer Actions:

- Cyber Insurance: Negotiate a minimum CAD 100M cyber liability policy covering first-party breach remediation, third-party regulatory fines, and class-action defense costs. This layer activates if mitigation controls fail.

## 5.2 R-02: Regulatory Approval Delay by OSFI / Minister of Finance (EMV: CAD 17.4M)

Response Category: Mitigate

A regulatory delay cannot be avoided or transferred, as the approval is a mandatory precondition for deal close under the Bank Act. The primary response is proactive regulatory engagement designed to minimize the probability of an extended review or conditional approval, and parallel contingency planning that reduces the financial cost of any delay that does occur.

Mitigation Actions:

- Proactive OSFI Engagement: Submit a comprehensive Bank Act Schedule I acquisition application with full pre-filing briefings to OSFI and the Minister of Finance. Include a detailed data-governance annex addressing PC Optimum data concentration concerns — the primary trigger for Competition Bureau scrutiny.

- External Regulatory Counsel: Retain a Canadian law firm with demonstrated M&A banking approval experience (e.g., prior Schedule I acquisition approvals) to lead the filing strategy and manage supplemental information requests.

- Contingency Scenario Planning: Prepare three integration pathway scenarios — 6-month, 9-month, and 12-month delay — with corresponding budget adjustments. Each scenario quantifies the additional carrying cost against the CAD 105M integration budget and adjusts the synergy realization timeline accordingly.

- Board Communication Protocol: Establish a monthly regulatory update cadence for the EQB Board and Loblaw's two board representatives, ensuring governance visibility into approval milestones and delay risks.

## 5.3 R-03: Customer Attrition from PC Financial Portfolio (EMV: CAD 33.0M)

Response Category: Mitigate

Customer attrition is the primary threat to the revenue thesis of the acquisition. The cross-sell opportunity (R-38) is directly undermined by every customer lost during the migration window: the addressable base for cross-sell conversion shrinks in proportion to attrition. The response strategy therefore prioritizes early customer communication and incentive deployment before and immediately after deal close, rather than reactive retention campaigns after churn has materialized.

Mitigation Actions:

- Pre-Close Communication Campaign: Launch a co-branded EQB/PC Financial customer communication initiative within 30 days of regulatory approval, explaining the transition timeline, benefit continuity, and new EQ Bank product access. Leverage Loblaw's existing PC Optimum notification infrastructure.

- PC Optimum Linkage as Retention Anchor: Immediately activate PC Optimum points-linked incentives for customers who adopt an EQ Bank savings or GIC product within 90 days of migration. This monetizes the loyalty ecosystem as a retention tool rather than purely a cross-sell vehicle.

- Competitive Response Playbook: Develop a pre-approved rapid-response marketing playbook for scenarios where Big Six banks or fintechs (Koho, Neo Financial) launch targeted campaigns at migrated PC Financial customers. Activation threshold: competitor product launch targeting the PC Optimum demographic.

- Monthly NPS Monitoring: Track Net Promoter Score among migrated customers monthly. I&W threshold: NPS decline >15 points within 60 days of migration triggers escalation to CMO and IMO with a mandatory 30-day response plan.

## 5.4 R-17: Fraud Spike During Integration (EMV: CAD 25.3M)

Response Category: Mitigate

Fraud during the integration window is operationally distinct from cybersecurity (R-01) in that it exploits customer-facing authentication confusion rather than system-level vulnerabilities. The primary response centers on enhanced identity verification and real-time transaction monitoring calibrated specifically to the dual-system period, when PC Financial and EQ Bank databases temporarily coexist.

Mitigation Actions:

- Enhanced Identity Verification for PC Financial Customers: Implement step-up authentication (multi-factor verification) for all PC Financial account holders during the migration window. Require identity re-verification for any high-value transaction or contact information change.

- Real-Time Fraud Detection Calibration: Retrain EQB's fraud detection models on PC Financial's customer behavioral baseline (transaction velocity, geography, merchant categories) before migration begins. The current model is calibrated for EQ Bank's savings-focused customer base and is not suited for credit card transaction patterns.

- Dedicated Integration Fraud Response Team: Establish a temporary surge team within EQB's fraud operations function, staffed for the 90-day peak integration window. This team handles escalated account takeover complaints from PC Financial customers under a dedicated case management queue.

- Card-Not-Present (CNP) Fraud Controls: PC Financial's 2+ million credit card accounts represent the highest-risk CNP fraud vector. Deploy 3DS2 authentication for all online card transactions during the migration period, with enhanced rules for first-time merchants.

## 5.5 R-38: Cross-Sell Conversion Opportunity (EMV: CAD +83.6M)

Response Category: Exploit (Maximize Upside)

As a positive risk, R-38 requires an 'exploit' strategy — deliberate actions to increase the probability and magnitude of the opportunity's realization, rather than simply accepting whatever conversion rate emerges. The I&W analysis estimated a base-case opportunity EMV of CAD +83.6 million (Monte Carlo simulation mean), with an optimistic ceiling of CAD +180 million if conversion targets are fully met across the 18-month integration period.

Exploit Actions:

- Structured 90-Day Cross-Sell Sprint: Launch a prioritized cross-sell campaign within 90 days of deal close, targeting the approximately 2.25 million PC Financial credit card holders who currently hold no deposit product. Campaign channels: PC Optimum app notifications, Loblaw in-store kiosk messaging, and EQ Bank's digital onboarding flow.

- PIPEDA-Compliant Data Integration: Establish a consented data-sharing framework between EQB and PC Optimum that enables personalized product offers without triggering PIPEDA compliance risk. Legal review of all data-use consents must be completed before campaign launch.

- Conversion Funnel Analytics: Deploy EQB's TDH-EQB Fabric analytics platform to track the cross-sell funnel from initial offer impression to product application to funded account. Monthly reporting to CMO and CDO with variance analysis against I&W milestone targets.

- Incentive Structuring: Offer time-limited PC Optimum bonus point incentives (e.g., 10,000 points) for customers who open an EQ Bank savings account within 90 days of migration. This directly converts loyalty program engagement into deposit acquisition at marginal cost relative to traditional customer acquisition.

# 6. Key Risk Indicators (KRIs) and Trigger Points for Action

Key Risk Indicators are quantitative metrics that serve as early warning signals for each identified risk, enabling EQB's Integration Management Office and senior leadership to monitor risk exposure in near real-time and invoke pre-approved response protocols before losses materialize. Each KRI below is grounded in the CRISP-DM methodology: the business problem and data sources were defined during risk identification; the KRI metric was developed during data understanding and modeling; and the trigger thresholds were calibrated using the I&W quantitative analysis and Monte Carlo simulation outputs.

Five KRIs are presented, one per priority risk, with thresholds corresponding to the Amber (monitor and escalate) and Red (invoke response protocol) warning levels established in the I&W analysis. The KRI owner is responsible for monitoring the metric, reporting against thresholds, and escalating when a trigger is breached.

## 6.1 KRI-01: Monthly High/Critical Security Incident Volume (R-01 Cybersecurity)

CRISP-DM Basis: Business Understanding — OSFI B-13 mandates real-time technology risk monitoring for Schedule I banks. Data Understanding — SOC log data, SIEM alerts, and third-party penetration test results. Modeling — anomaly detection thresholds derived from EQB's pre-integration SOC baseline and benchmarked against Canadian financial sector breach frequency data (OSFI, 2022).

| KRI Metric | Green (Normal) | Amber (Watch) | Red (Act) |
| --- | --- | --- | --- |
| High/Critical SOC alerts per month | <3 incidents | 3–4 incidents | ≥5 incidents |
| Unauthorized access attempts on migration endpoints | <10/month | 10–19/month | ≥20/month |

Trigger Action — Amber: CISO notified within 24 hours; third-party security firm placed on standby; migration timeline reviewed for vulnerability windows.

Trigger Action — Red: Executive incident response team convened; OSFI notification protocol initiated; migration halted pending security audit.

Data Sources: Azure Security Center, SIEM platform (Microsoft Sentinel), third-party penetration test reports, OSFI incident reporting portal.

Reporting Frequency: Weekly during active integration window; monthly thereafter.

KRI Owner: CISO / Integration Management Office

## 6.2 KRI-02: Regulatory Approval Timeline Elapsed (R-02 Regulatory Delay)

CRISP-DM Basis: Business Understanding — Bank Act S.I. acquisition approvals have historically ranged from 90 to 270 days in Canada. Data Understanding — OSFI application submission date (January 2026); Competition Bureau filing date. Modeling — elapsed days since filing used as the primary leading indicator, with supplemental information requests (SIRs) as a secondary signal of regulatory concern.

| KRI Metric | Green (Normal) | Amber (Watch) | Red (Act) |
| --- | --- | --- | --- |
| Business days elapsed since OSFI filing without approval | <120 days | 120–179 days | ≥180 days |
| Supplemental information requests (SIRs) received from regulators | 0 | 1 SIR | ≥2 SIRs |

Trigger Action — Amber: Chief Legal Officer and General Counsel conduct weekly call with OSFI regulatory counsel; Board notified; contingency delay scenario activated.

Trigger Action — Red: External regulatory counsel engaged for SIR response within 10 business days; CFO models 6-month and 9-month delay budget impact; Board receives formal written update.

Data Sources: OSFI application tracking system, Competition Bureau case management portal, legal counsel communications.

Reporting Frequency: Bi-weekly from filing date.

KRI Owner: Chief Legal Officer / Chief Risk Officer

## 6.3 KRI-03: Monthly Customer Churn Rate — Migrated PC Financial Portfolio (R-03 Attrition)

CRISP-DM Basis: Business Understanding — Customer attrition directly erodes the cross-sell addressable base. A 5% attrition rate across 2.5 million customers represents 125,000 lost customers at ~CAD 400 LTV each (~CAD 50M foregone value). Data Understanding — PC Financial legacy CRM system, EQ Bank's digital banking platform account closure records, NPS survey data. Modeling — Monthly churn rate and NPS delta modeled using logistic regression on historical PC Financial customer behavior data; thresholds calibrated to EMV sensitivity analysis from Monte Carlo simulation.

| KRI Metric | Green (Normal) | Amber (Watch) | Red (Act) |
| --- | --- | --- | --- |
| Monthly churn rate — migrated PC Financial customers | <1.5% | 1.5%–3.0% | >3.0% |
| NPS delta (change from pre-migration baseline) | 0 to –5 pts | –6 to –14 pts | ≥–15 pts |

Trigger Action — Amber: CMO reviews retention messaging; PC Optimum incentive offer escalated to all at-risk segments; competitive activity scan initiated.

Trigger Action — Red: Crisis retention playbook activated; emergency PC Optimum bonus offer deployed; IMO convenes cross-functional response team within 48 hours; CFO reassesses cross-sell revenue projections.

Data Sources: EQ Bank core banking platform (Temenos), CRM system, NPS survey platform, PC Optimum engagement data.

Reporting Frequency: Monthly post-migration; weekly during first 90 days.

KRI Owner: CMO / Chief Customer Experience Officer

## 6.4 KRI-04: Fraud Incident Rate vs. Pre-Integration Baseline (R-17 Fraud Spike)

CRISP-DM Basis: Business Understanding — PC Financial's credit card portfolio introduces Card-Not-Present (CNP) fraud exposure that EQB's current fraud detection models are not calibrated for. Data Understanding — EQB baseline fraud rate (pre-integration), PC Financial historical fraud data, account takeover complaint logs. Modeling — Fraud rate expressed as month-over-month percentage change versus pre-integration baseline; retrained fraud detection model (Random Forest) identifies anomalous transaction clusters above threshold.

| KRI Metric | Green (Normal) | Amber (Watch) | Red (Act) |
| --- | --- | --- | --- |
| Monthly fraud incident rate vs. pre-integration baseline | <+10% | +10% to +39% | ≥+40% |
| Confirmed identity fraud losses in a single month | <CAD 250K | CAD 250K–999K | ≥CAD 1M |

Trigger Action — Amber: Fraud operations team reviews top-loss merchant categories; 3DS2 authentication rules tightened for flagged transaction patterns; Fraud Prevention Lead briefs CRO.

Trigger Action — Red: Dedicated integration fraud response team activated; OSFI fraud reporting initiated; affected customers notified within 24 hours; CNP transaction velocity limits reduced system-wide.

Data Sources: EQB transaction monitoring system, PC Financial fraud management platform, identity verification provider logs (e.g., Equifax, TransUnion APIs), OSFI fraud reporting registry.

Reporting Frequency: Weekly during integration window; monthly post-stabilization.

KRI Owner: Chief Risk Officer / Fraud Prevention Lead

## 6.5 KRI-05: Cross-Sell Conversion Rate — PC Financial Cardholders (R-38 Opportunity)

CRISP-DM Basis: Business Understanding — Cross-sell conversion is the primary revenue driver of the acquisition's financial rationale; 15%+ cumulative conversion at 18 months is EQB's internal target (approximately 337,500 net new EQ Bank product accounts from the PC Financial base). Data Understanding — EQ Bank account opening records, PC Optimum engagement data, mobile app download analytics. Modeling — Conversion rate modeled as a binomial distribution; I&W milestones calibrated against PERT 3-point estimates (Optimistic: CAD 180M, Most Likely: CAD 100M, Pessimistic: CAD 30M) from Monte Carlo simulation.

| KRI Metric | Green (On Track) | Amber (Behind) | Red (Underperforming) |
| --- | --- | --- | --- |
| Cumulative cross-sell conversion rate at 18 months | ≥15% | 8%–14.9% | <8% |
| EQ Bank app downloads among PC Financial cardholders (MoM growth) | ≥+5% MoM for 3+ months | +1% to +4.9% MoM | Flat or declining |

Trigger Action — Amber: CMO and CDO review conversion funnel analytics; underperforming channels de-prioritized; PC Optimum incentive offer refreshed. Revenue projections revised downward in IMO dashboard.

Trigger Action — Red: Full cross-sell strategy review convened with CEO and CFO; PC Optimum data partnership utilization audited for PIPEDA compliance barriers; EQB's long-term ROE target timeline extended; Board informed.

Data Sources: EQ Bank core banking platform, TDH-EQB Fabric analytics platform, PC Optimum engagement APIs, mobile app analytics (Firebase/App Store).

Reporting Frequency: Monthly; quarterly deep-dive to Board.

KRI Owner: CMO / Chief Digital Officer

# 7. Conclusion

The acquisition of PC Financial by EQB Inc. represents one of the most consequential strategic transactions in Canadian challenger banking history. This enterprise risk management assessment has examined the acquisition through a structured, analytics-driven lens, progressing from qualitative risk identification and prioritization through to quantitative I&W analysis, Machine Learning-based prediction, Monte Carlo simulation, and an integrated risk response framework grounded in CRISP-DM methodology.

The 40-risk register identified a diverse landscape of exposures spanning operational, regulatory, financial, strategic, legal, and reputational dimensions. Of these, seven risks scored in the High priority tier (score ≥45), with R-01 Cybersecurity Breach and R-38 Cross-Sell Conversion Opportunity both reaching the maximum score of 81 — a striking finding that the acquisition's greatest threat and greatest upside are inseparably linked to the same integration process.

The quantitative assessment produced three key findings that should inform EQB's Integration Management Office and Board decision-making throughout 2026:

- The combined Monte Carlo simulation mean across four threat risks (R-01, R-02, R-03, R-17) is CAD 120.2 million — representing the recommended minimum contingency reserve. This figure exceeds EQB's disclosed CAD 105 million integration budget, meaning that integration cost overruns and risk-related losses, if they materialize concurrently, could substantially pressure EQB's financial position during an already-fragile post-restructuring period.

- R-01 Cybersecurity carries a disproportionate share of total threat EMV (CAD 68.5M of the CAD 144.1M total), reflecting the catastrophic tail risk of a breach during the integration window. The Monte Carlo simulation's 95th percentile for R-01 alone approaches CAD 180 million — more than twice the deal's annual synergy target. This makes cybersecurity investment not merely a compliance obligation but the single highest-ROI risk mitigation in EQB's integration budget.

- The cross-sell opportunity (R-38) has an EMV of CAD +83.6 million under the Monte Carlo simulation's central estimate, rising to CAD +180 million in the optimistic scenario. This is the financial foundation of EQB's CAD 800 million acquisition price and its stated 15%+ ROE target. Every percentage point of customer attrition (R-03) directly reduces this opportunity base — underscoring why the risk response strategies for R-03 and R-38 must be operationally coordinated, not managed in isolation.

The five Key Risk Indicators defined in Section 6 translate these quantitative findings into actionable monitoring metrics, with Amber and Red thresholds that provide EQB's leadership team with structured escalation pathways before losses materialize. The KRI framework is designed to be embedded within EQB's existing risk governance infrastructure — the CISO, CRO, CMO, and CLO each own specific indicators — ensuring accountability is distributed appropriately across the executive team.

From an Integrated Situation Assessment perspective, the acquisition's risk landscape is shaped by both business environment factors (intense competition from Canada's Big Six banks and fintechs, EQB's post-restructuring financial pressure, and the structural dependency on the Loblaw commercial partnership) and non-business environment factors (OSFI and Competition Bureau regulatory oversight, PIPEDA privacy compliance requirements, macroeconomic interest rate sensitivity, and the evolving Canadian cybersecurity threat landscape). These factors do not operate independently — regulatory delay amplifies competitive vulnerability, cybersecurity exposure is shaped by OSFI mandates and adversarial market dynamics, and cross-sell success depends on the regulatory latitude granted to EQB's use of PC Optimum data. The risk responses and KRIs in this report explicitly account for these interdependencies.

If EQB executes its integration with the discipline that this risk assessment prescribes — particularly on cybersecurity, customer retention, and cross-sell conversion — the acquisition of PC Financial has the potential to deliver what CEO Chadwick Westlake described as "a new era for banking in Canada." The quantitative evidence supports that aspiration: the net risk-adjusted value of the deal remains strongly positive. But that outcome is not guaranteed. It is conditional on EQB treating the 2026 integration window not as a project management exercise, but as an enterprise risk management challenge of the highest order.

# Appendix 1: Complete Risk Treatment and Response Plan (RT&RP)

The following table presents the complete 40-risk register for the EQB Inc. / PC Financial acquisition, incorporating all risk identification, scoring, qualitative prioritization, and quantitative I&W / Monte Carlo updates. Risks are sorted by Risk Score (descending). Positive risks are marked with ★. Priority thresholds: High ≥45, Medium 21–44, Low ≤20.

| Risk # | Risk Description | L | I | Score | Pri. | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Cybersecurity breach during IT system integration | 9 | 9 | 81 | H | Implement zero-trust architecture; conduct pre-migration penetration testing; engage third-party cybersecurity auditors; align with OSFI B-13 | CISO / IMO | Open |
| ★R-38 | Cross-sell conversion opportunity — PC Financial credit-card customers | 9 | 9 | 81 | H | Launch 90-day cross-sell campaign post-close; use PC Optimum loyalty data for personalized offers; PIPEDA-compliant consent framework; set quarterly KPIs | CMO / CDO | Open |
| R-03 | Customer attrition from PC Financial portfolio post-migration | 7 | 8 | 56 | H | Launch early customer communication; retain PC Financial branding during transition; offer loyalty incentives to migrating customers | CMO / CX | Open |
| R-14 | PIPEDA / privacy compliance failure due to expanded data migration | 7 | 8 | 56 | H | Appoint Privacy Officer for integration; conduct PIPEDA compliance audit of PC Optimum data-sharing agreements; deploy consent management platform | CPO / Legal | Open |
| ★R-39 | Omnichannel expansion opportunity — Loblaw retail network opens physical presence | 7 | 8 | 56 | H | Activate Loblaw kiosk banking partnership within 60 days; train Loblaw staff on EQ Bank products; deploy in-store EQ Bank account opening capability | COO / CDO | Open |
| ★R-40 | AI personalization opportunity — PC Optimum spending data drives targeted product offers | 7 | 8 | 56 | H | Integrate PC Optimum data with TDH-EQB Fabric; build AI personalization models on combined dataset; establish PIPEDA-compliant data governance | Chief Data Officer | Open |
| R-17 | Fraud spike during transition — account takeover and identity fraud | 9 | 6 | 54 | H | Deploy real-time fraud detection across dual-system period; step-up MFA for PC Financial customers; 3DS2 for all CNP transactions; dedicated fraud team | CRO / Fraud Lead | Open |
| R-05 | Key talent loss — PC Financial staff exit during transition uncertainty | 9 | 4 | 36 | M | Retention bonus program for critical PC Financial staff (12-month cliff); early culture integration sessions; clear career pathing within EQB | CHRO / IMO | Open |
| R-06 | Brand confusion / reputational damage during PC Financial rebrand | 7 | 6 | 42 | M | Phased rebrand strategy; retain PC Financial brand during first 12 months; proactive media strategy | CMO | Open |
| R-07 | Integration cost overrun beyond the $105M budget | 7 | 6 | 42 | M | Monthly IMO budget tracking; ±10% contingency built into integration budget; CFO approval required for scope changes | CFO / IMO | Open |
| R-15 | Competitive poaching of PC Financial customers by Big Six or fintechs | 7 | 6 | 42 | M | Competitive intelligence monitoring; pre-approved counter-offer playbooks; PC Optimum incentive refresh for at-risk segments | CMO / Strategy | Open |
| R-26 | Failure to achieve $30M annual cost synergy targets | 7 | 6 | 42 | M | Detailed synergy tracking dashboard; quarterly CFO review; identify backup synergy levers (e.g., vendor renegotiation, headcount optimization) | CFO / IMO | Open |
| R-31 | Loss of PC Optimum co-branding benefits due to loyalty program restructuring | 7 | 6 | 42 | M | Lock 12-year exclusivity terms in commercial agreement with Loblaw; include change-of-control provisions | CLO / CFO | Open |
| R-08 | Loblaw co-dependency disruption — operational complexity of embedded partnership | 5 | 8 | 40 | M | Formalize SLAs with Loblaw for all operational dependencies; establish joint governance committee; quarterly relationship review | COO / CLO | Open |
| R-09 | Cross-sell conversion failure — EQB fails to upsell PC Financial customers | 5 | 8 | 40 | M | Monthly cross-sell funnel analytics; A/B test offer messaging; activate KRI-05 thresholds | CMO / CDO | Open |
| R-10 | Interest rate sensitivity affecting mortgage portfolio profitability | 5 | 8 | 40 | M | Hedge interest rate exposure; maintain fixed/variable mortgage product mix; quarterly ALM review | CFO / Treasury | Open |
| R-13 | Credit quality deterioration — PC Financial loan book has higher risk profiles | 5 | 8 | 40 | M | Pre-close credit portfolio deep-dive; stress test loan book for 200bps rate shock; provision adequately at close | CRO / Finance | Open |
| R-28 | Change management fatigue — internal teams overwhelmed by integration demands | 7 | 4 | 28 | M | Establish IMO with dedicated integration PMs; protect BAU operations from integration scope creep; monthly staff wellbeing pulse | CHRO / IMO | Open |
| R-19 | HR integration friction — misaligned compensation, benefits, and culture | 7 | 4 | 28 | M | Conduct HR parity analysis pre-close; align compensation bands within 90 days; launch joint culture workstream | CHRO | Open |
| R-12 | Third-party vendor / contract disputes — Loblaw-side service agreements | 5 | 6 | 30 | M | Audit all third-party contracts for change-of-control clauses; renegotiate Loblaw-linked agreements pre-close | CLO / Procurement | Open |
| R-21 | Loblaw relationship souring — residual commercial dependencies create friction | 5 | 6 | 30 | M | Maintain joint EQB-Loblaw steering committee; quarterly relationship health assessment; include dispute resolution mechanism in commercial agreement | CEO / CLO | Open |
| R-23 | Adverse media coverage amplifying customer churn during any integration incident | 5 | 6 | 30 | M | Pre-approved crisis communication playbook; media monitoring dashboard; PR firm on retainer during integration | CMO / Communications | Open |
| R-30 | Underestimating IT infrastructure age — legacy PC Financial systems | 5 | 6 | 30 | M | Conduct pre-close technology infrastructure audit; allocate dedicated legacy remediation budget in IMO plan | CTO / IMO | Open |
| R-04 | Data migration failure or corruption of customer records | 3 | 9 | 27 | M | Full data backup before each migration tranche; parallel-run validation for 30 days post-migration; rollback plan in place | CTO / CISO | Open |
| R-32 | Geopolitical or macro shock — recession or housing market crash | 3 | 9 | 27 | M | Maintain capital buffer above OSFI minimum; stress test combined balance sheet annually; diversify mortgage geographic exposure | CFO / CRO | Open |
| R-11 | Regulatory capital requirement changes by OSFI post-close | 3 | 8 | 24 | M | Monitor OSFI capital guidance updates; maintain CET1 ratio at minimum 50bps above regulatory minimum | CFO / CRO | Open |
| R-02 | Regulatory approval delay by OSFI / Minister of Finance | 3 | 8 | 24 | M | Proactive OSFI engagement; external regulatory counsel; contingency delay scenarios (6, 9, 12 months) | CLO / CRO | Open |
| R-18 | Inaccurate due diligence — hidden non-performing loans surface post-close | 3 | 8 | 24 | M | Enhanced credit quality review as condition of close; reps and warranties insurance; 90-day post-close audit | CRO / Finance | Open |
| R-20 | Liquidity risk from deposit runoff — unexpected withdrawal surge post-migration | 3 | 8 | 24 | M | Maintain HQLA buffer; monitor deposit runoff KPI daily during first 90 days; activate OSFI liquidity reporting | Treasurer / CRO | Open |
| R-27 | AML compliance gaps — PC Financial anti-money laundering controls | 3 | 8 | 24 | M | AML audit of PC Financial controls pre-close; align to FINTRAC standards; retrain staff | CCO / CRO | Open |
| R-37 | EQB credit rating downgrade due to acquisition leverage | 3 | 8 | 24 | M | Maintain leverage ratios within OSFI and rating agency guidance; schedule proactive rating agency briefings post-close | CFO | Open |
| R-16 | Operational downtime during system cutover | 3 | 6 | 18 | L | Schedule cutovers during low-traffic periods; test rollback procedures; customer communication protocol for planned outages | CTO / IMO | Open |
| R-22 | Legal challenges from PC Financial employees — wrongful dismissal | 3 | 6 | 18 | L | Follow Employment Standards Act obligations; engage labour counsel for workforce transition planning | CHRO / CLO | Open |
| R-24 | Mis-selling or product suitability complaints from PC Financial customers | 3 | 6 | 18 | L | Train EQB frontline staff on PC Financial product suitability standards; implement complaints monitoring dashboard | CCO / CMO | Open |
| R-33 | Insurance and indemnity gaps — reps and warranties coverage inadequate | 3 | 6 | 18 | L | Review R&W insurance policy limits; confirm coverage for all material risk categories identified in due diligence | CLO / CFO | Open |
| R-35 | AI-driven personalization producing biased or discriminatory outcomes | 3 | 6 | 18 | L | Implement AI ethics review for all personalization models; conduct pre-deployment bias audits; align to OSFI AI guidance | CDO / CCO | Open |
| R-36 | TDH-EQB Fabric analytics platform fails to scale to 3.5M customer base | 3 | 6 | 18 | L | Conduct load testing on TDH-EQB Fabric at 5x current volume before migration; cloud auto-scaling rules in place | CTO / CDO | Open |
| R-25 | Technology vendor lock-in — EQB inherits legacy PC Financial contracts | 5 | 4 | 20 | L | Inventory all PC Financial vendor contracts; identify exit clauses; prioritize Temenos consolidation to reduce vendor complexity | CTO / Procurement | Open |
| R-29 | ESG / reputational risk — environmental or social controversy associated with Loblaw | 5 | 4 | 20 | L | Define ESG boundaries in commercial agreement; monitor Loblaw ESG events; prepare EQB-specific ESG communications | CEO / Communications | Open |
| R-34 | Governance integration lag — PC Financial board and committee structures | 3 | 4 | 12 | L | Appoint EQB board integration committee within 30 days of close; complete governance integration within 90 days | Board / General Counsel | Open |

Priority Key: H = High (Score ≥45) | M = Medium (Score 21–44) | L = Low (Score ≤20) | ★ = Positive Risk (Opportunity)

# References

Defense World. (2026, January 8). EQB conference: CEO targets operating leverage, 12%+ ROE in 2026, PC Financial deal boosts scale. https://www.defenseworld.net/2026/01/08/

EQB Inc. (2025, December 3). EQB redefines challenger banking in Canada with agreement to acquire PC Financial from Loblaw. CNW/Investor Room. https://eqb.investorroom.com/2025-12-03-EQB

EQB Inc. (2026, February 25). EQB reports first quarter 2026 results. PR Newswire. https://www.prnewswire.com/news-releases/eqb-reports-first-quarter-2026-results-302697609.html

Fintech Futures. (2025, December 8). EQB to acquire PC Financial in $800m deal. https://www.fintechfutures.com/m-a/eqb-to-acquire-pc-financial-in-800m-deal

Government of Canada. (2000). Personal Information Protection and Electronic Documents Act (PIPEDA), S.C. 2000, c. 5. https://laws-lois.justice.gc.ca/eng/acts/P-8.6/

Investing.com. (2025, December 4). Earnings call transcript: EQB Inc Q4 2025 misses EPS forecast, stock surges. https://www.investing.com/news/transcripts/

Office of the Superintendent of Financial Institutions. (2022). Guideline B-13: Technology and cyber risk management. Government of Canada. https://www.osfi-bsif.gc.ca/en/guidance/guidance-library/technology-cyber-risk-management-guideline

Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK Guide) (7th ed.). PMI.

Temenos. (2025). EQ Bank success story. https://www.temenos.com/success-story/eq-bank-success-story/