## Sheet1
Negative Risks >=45
ID | Description | I) | Strategy | Justification | Actions
R-03 | Customer attrition from PC Financial portfolio post-migration | L=7 × I=8 = 56 HIGH | Mitigate | ROOT CAUSE: ~90% of PC Financial's 2M+ credit card holders have never had a deposit relationship with EQB they know PC Financial through Loblaw checkouts, PC Optimum points, and President's Choice branding. EQB is an unfamiliar digital-only bank to them. TD, RBC, Koho, and Neo Financial are actively watching for this window to poach customers with targeted rate offers and sign-up bonuses. WHY MITIGATE: EQB paid ~CAD 800M for this customer base. Losing even 10% of the 3.5M migrated customers = 350,000 lost relationships, each representing a cross-sell pipeline that underpins EQB's projected EPS accretion. Acceptance is commercially indefensible. Avoidance = no migration = no deal value. CMO / Customer Experience owns this directly. WHY NOT TRANSFER: You cannot insure against customer decisions. The only lever is making EQB's value proposition so tangible and concrete during the migration window that leaving costs more than staying. | 1. DUAL-BRAND "PC FINANCIAL ¦ POWERED BY EQ BANK" FOR MINIMUM 12 MONTHS: Every touchpoint Loblaw kiosk screens, in-app header, monthly statement, ATM receipt shows both logos. No abrupt EQ Bank-only rebrand until NPS tracking among migrated customers crosses 65% EQ Bank brand recognition. Measured monthly by the CMO team. 2. PC OPTIMUM POINTS CONTINUITY GUARANTEE IN WRITING: The single biggest anxiety PC Financial customers will have is "do I lose my PC Optimum points?" Publish a legally binding guarantee within 7 days of deal announcement: all accrued PC Optimum points transfer intact, earn rates are unchanged for 12 months post-migration. Delivered via personalized in-app notification and physical mail to all 3.5M customers. 3. NO ATM FEES AT ANY INTERAC-CONNECTED ATM IN CANADA FOR 90 DAYS POST-MIGRATION: EQ Bank normally reimburses ATM fees anyway, but make this explicit and proactive not buried in fine print. PC Financial customers currently use 500+ PC Financial/Loblaw ATMs. During migration, guarantee zero ATM fees at any Canadian Interac machine for 90 days so customers never feel stranded. Cost to EQB is minimal; retention signal is strong. 4. MIGRATION WELCOME HISA RATE 4.5% LOCKED FOR 6 MONTHS: Koho offers 3.5%, Neo Financial 4%, TD eSavings 2.25%. EQB's standard HISA is already competitive. Lock migrating customers into a named "Migration Welcome Rate" of 4.5% for 6 months published with a clear expiry date so it feels like a real offer, not a standard product. This directly neutralizes the rate-shopping window that TD and Koho will exploit. 5. WEEKLY DEPOSIT OUTFLOW KRI AT 1.5% THRESHOLD WITH PRE-WRITTEN PLAYBOOK: Do not wait until attrition is visible in quarterly results. Set a real-time KRI: if net weekly deposit outflow from migrated PC Financial accounts exceeds 1.5%, the CMO and CRO present a joint retention response plan to the CEO within 48 hours. The response playbook including an emergency rate offer and targeted outreach campaign is written and approved before migration day, not drafted reactively.