## Sheet1
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Risk Score | Priority (H, M, L) | Mitigation | Risk Owner | Open/Closed
R-01 | 2025-12-16 | Cybersecurity breach during IT system integration | Merging EQB and PC Financial banking platforms creates exploitable vulnerabilities in APIs, data pipelines, and access controls during cutover | Unauthorized access to 3.5M+ customer financial records, system outages, and OSFI B-13 sanctions | Regulatory fines, breach remediation costs, customer trust erosion, and potential class-action liability | 9 | 9 | 81 | H | Implement zero-trust architecture; conduct pre-migration penetration testing; engage third-party cybersecurity auditors; align with OSFI B-13 Technology Risk guidelines | Chief Information Security Officer (CISO) | Open
R-02 | 2025-12-16 | Regulatory approval delay by OSFI / Minister of Finance | Complex deal requiring Schedule I bank-linked entity acquisition under the Bank Act, triggering multi-regulator review | Delayed deal close beyond 2026 target, prolonged operational limbo and staff/customer uncertainty | Integration cost escalation, reputational uncertainty, and potential deal renegotiation or termination | 3 | 8 | 24 | M | Proactive engagement with OSFI and Minister of Finance; retain regulatory counsel; submit comprehensive application with full disclosure | Chief Legal Officer / Regulatory Affairs | Open
R-03 | 2025-12-16 | Customer attrition from PC Financial portfolio post-migration | PC Financial customers unfamiliar with EQB brand during rebranding may switch to competitors (TD, RBC, Koho, Neo Financial) | Deposit outflow and reduced portfolio size, undermining the acquisition's strategic rationale | Revenue shortfall, reduced cross-sell base, and lower EPS accretion for EQB shareholders | 7 | 8 | 56 | H | Launch early customer communication campaign; retain PC Financial branding during transition; offer loyalty incentives to migrating customers | Chief Marketing Officer / Customer Experience | Open
R-04 | 2025-12-16 | Data migration failure or corruption of customer records and transaction history | Transfer of 3.5M+ customer records and loan files across legacy PC Financial systems to EQB's Temenos platform | Data loss, transaction errors, service outages, and regulatory scrutiny over data integrity | Operational disruption, customer harm, potential regulatory sanctions under OSFI, and reputational damage | 3 | 9 | 27 | M | Conduct parallel-run testing; establish rollback protocols; engage Temenos specialists; conduct data reconciliation audits pre- and post-cutover | Chief Technology Officer / Integration PMO | Open
R-05 | 2025-12-16 | Key talent loss PC Financial staff exit during transition uncertainty | Uncertainty about role redundancy, compensation alignment, and cultural differences prompts key PC Financial staff to leave | Loss of institutional knowledge, operational gaps, and increased contractor dependency | Integration delays, elevated HR costs, and reduced integration execution quality | 9 | 4 | 36 | M | Implement retention bonuses for critical roles; communicate clear career pathways within 30 days of announcement; align HR policies within 90 days of close | Chief People Officer / HR Integration Lead | Open
R-06 | 2025-12-16 | Brand confusion / reputational damage during PC Financial rebrand to EQ Bank | Customers unsure who holds their deposits after branding changes from PC Financial to EQ Bank may lose confidence | Customer confusion driving attrition, media scrutiny, and reduced trust in EQB as a deposit-taking institution | Reputational harm, deposit outflow, and long-term brand dilution for the EQ Bank franchise | 7 | 6 | 42 | M | Develop phased brand transition plan with co-branding period; invest in targeted customer education campaigns; monitor brand sentiment in real-time | Chief Marketing Officer / Brand | Open
R-07 | 2025-12-16 | Integration cost overrun beyond the $105M budget | Underestimation of IT infrastructure age, vendor contract complexities, HR integration friction, and legal/regulatory costs | Actual integration spend exceeds projected $105M, compressing deal economics | Pressure on near-term earnings, EPS dilution, and shareholder dissatisfaction | 7 | 6 | 42 | M | Establish integration management office (IMO) with milestone-based budget tracking; conduct independent cost audit pre-close; maintain 15% contingency reserve | Chief Financial Officer / Integration PMO | Open
R-08 | 2025-12-16 | Loblaw co-dependency disruption operational complexity of exiting Loblaw store infrastructure | PC Financial operates through ~2,500 Loblaw kiosk locations; unwinding this relationship is operationally complex and contractually uncertain | Disruption to in-store banking services, loss of distribution channel, and customer access gaps | Revenue loss from disrupted service delivery, operational gaps, and customer attrition tied to in-store banking | 5 | 8 | 40 | M | Negotiate structured wind-down agreement with Loblaw pre-close; develop alternative digital and ATM-based service delivery model for affected customers | Chief Operating Officer / Partnerships | Open
R-09 | 2025-12-16 | Cross-sell conversion failure EQB fails to upsell PC Financial customers into EQB products | PC Financial customers have limited awareness of EQB's mortgage and savings products; cross-sell conversion may be lower than modeled | Below-forecast revenue uplift and weakened business case for the acquisition | EPS accretion shortfall and investor disappointment if synergy targets tied to cross-sell are missed | 5 | 8 | 40 | M | Invest in AI-driven personalization using PC Optimum data; design frictionless product onboarding flows; set cross-sell KPI targets with monthly tracking post-close | Chief Revenue Officer / Digital Banking | Open
R-10 | 2025-12-16 | Interest rate sensitivity affecting mortgage portfolio profitability post-acquisition | Volatile Bank of Canada rate environment may compress net interest margin on EQB's mortgage-heavy combined portfolio | Reduced profitability from combined lending portfolio, undermining deal revenue model assumptions | Lower earnings, impaired deal economics, and investor concern over margin performance | 5 | 8 | 40 | M | Implement interest rate hedging strategy; diversify product mix; model multiple rate scenarios in deal economics | Chief Financial Officer / Treasury | Open
R-11 | 2025-12-16 | Regulatory capital requirement changes OSFI imposes new capital buffers on combined entity | OSFI may impose additional capital adequacy requirements on EQB following the acquisition of a significantly larger deposit base | Constrained capital available for lending and growth, reducing return on equity | Strategic flexibility reduction, potential need for equity raise, and pressure on EQB's capital ratios | 3 | 8 | 24 | M | Engage OSFI proactively; model capital scenarios under conservative OSFI buffer assumptions; maintain strong CET1 ratio pre-close | Chief Financial Officer / Capital Management | Open
R-12 | 2025-12-16 | Third-party vendor / contract disputes Loblaw-side service agreements not transferring cleanly | Vendor contracts held by Loblaw on behalf of PC Financial may not be assignable to EQB, requiring renegotiation or termination | Service continuity gaps and unexpected vendor renegotiation costs post-close | Operational disruption, elevated vendor costs, and potential litigation from contract disputes | 5 | 6 | 30 | M | Conduct comprehensive vendor contract review in due diligence; engage legal counsel to assess assignability; renegotiate key vendor agreements pre-close | Chief Legal Officer / Vendor Management | Open
R-13 | 2025-12-16 | Credit quality deterioration PC Financial loan book has higher default risk than disclosed | PC Financial's credit card and loan portfolio may carry higher-than-disclosed delinquency rates or undisclosed credit quality issues | Elevated loan loss provisions and write-offs post-acquisition | Financial losses, OSFI scrutiny, and impaired deal economics if credit losses exceed modeled assumptions | 5 | 8 | 40 | M | Conduct granular credit due diligence; stress-test portfolio under adverse scenarios; implement enhanced credit monitoring post-close; align underwriting standards | Chief Risk Officer / Credit Risk | Open
R-14 | 2025-12-16 | PIPEDA / privacy compliance failure due to expanded data migration scope | Integrating PC Optimum loyalty data with EQB banking data expands personal data processing scope, increasing PIPEDA obligations | OPC regulatory investigation, mandatory breach disclosure, and customer privacy complaints | Regulatory fines, reputational harm, and operational remediation costs | 7 | 8 | 56 | H | Conduct pre-integration Privacy Impact Assessment; appoint dedicated Privacy Officer for integration; align data sharing with PIPEDA consent requirements | Chief Privacy Officer / Compliance | Open
R-15 | 2025-12-16 | Competitive poaching of PC Financial customers by Big Six or fintechs during transition | TD, RBC, and fintechs (Koho, Neo Financial) aggressively target 3.5M PC Financial customers during the brand transition period | Customer poaching and market share loss before EQB establishes its value proposition with acquired base | Reduced cross-sell revenue opportunity and weakened competitive positioning | 7 | 6 | 42 | M | Accelerate customer communication and EQ Bank product onboarding; launch targeted retention offers; monitor competitor activity in real-time | Chief Marketing Officer / Product | Open
R-16 | 2025-12-16 | Operational downtime during system cutover | Migration of banking services from PC Financial legacy systems to EQB's Temenos platform requires planned service interruptions | Customers unable to access accounts, make payments, or use credit cards during cutover windows | Customer frustration, attrition, regulatory complaint risk, and reputational damage | 3 | 6 | 18 | L | Schedule cutover during lowest-traffic windows; pre-notify customers; maintain fallback channels; limit cutover windows to under 4 hours | Chief Technology Officer / Integration PMO | Open
R-17 | 2025-12-16 | Fraud spike during transition account takeover and identity fraud exploiting integration confusion | Integration-related system changes and customer notification activity create phishing and social engineering opportunities for fraudsters | Elevated account takeover fraud and customer financial losses during transition period | Financial losses, customer harm, regulatory scrutiny, and reputational damage | 9 | 6 | 54 | H | Deploy enhanced fraud monitoring during integration; implement step-up authentication; proactively warn customers about phishing attempts | Chief Risk Officer / Fraud Prevention | Open
R-18 | 2025-12-16 | Inaccurate due diligence hidden non-performing loans surfacing post-close | Time and information constraints in due diligence may allow undisclosed non-performing loans or contingent liabilities to go undetected | Unexpected credit losses and provisions post-close reducing deal value | Financial write-downs, investor surprise, and management credibility risk if undisclosed liabilities surface | 3 | 8 | 24 | M | Conduct granular loan-level due diligence; engage independent credit review firm; negotiate reps and warranties coverage for undisclosed liabilities | Chief Risk Officer / M&A Advisory | Open
R-19 | 2025-12-16 | HR integration friction misaligned compensation, benefits, and culture between two firms | Compensation structure, benefits packages, and cultural norms differ significantly between EQB and PC Financial | Employee dissatisfaction, grievances, and integration friction delaying operational normalization | Elevated HR costs, morale decline, reduced productivity, and integration delays | 7 | 4 | 28 | M | Conduct cultural assessment pre-close; harmonize compensation bands within 90 days; establish joint integration task force with employee representation | Chief People Officer / HR Integration Lead | Open
R-20 | 2025-12-16 | Liquidity risk from deposit runoff unexpected withdrawal surge if customer confidence wavers | Negative media coverage or customer uncertainty during integration may trigger unexpected deposit withdrawals from the combined entity | Liquidity pressure requiring emergency funding or asset sales to meet withdrawal demands | Liquidity stress, potential regulatory intervention, and reputational damage if funding gaps emerge | 3 | 8 | 24 | M | Maintain liquidity buffers above OSFI minimums; prepare contingency funding plan; implement real-time deposit monitoring during integration | Chief Financial Officer / Treasury | Open
R-21 | 2025-12-16 | Loblaw relationship souring residual commercial dependencies create ongoing negotiation friction | Post-close commercial dependencies (kiosks, PC Optimum data, transition services) create ongoing negotiation points with Loblaw that may become contentious | Stalled transition services, unresolved commercial disputes, and operational dependencies persisting beyond planned timelines | Integration delays, elevated transition costs, and governance risk from ongoing Loblaw influence | 5 | 6 | 30 | M | Negotiate detailed transition service agreements (TSAs) with Loblaw pre-close; set firm expiry dates for all TSAs; appoint dedicated relationship manager for Loblaw commercial dealings | Chief Operating Officer / Legal | Open
R-22 | 2025-12-16 | Legal challenges from PC Financial employees wrongful dismissal or class actions during integration | Workforce restructuring and role eliminations during integration may trigger wrongful dismissal claims or class action lawsuits | Litigation costs, management distraction, and potential delays to integration execution | Financial liability, reputational harm, and operational distraction during a critical integration period | 3 | 6 | 18 | L | Engage employment law counsel before any restructuring actions; follow severance policy strictly; document all workforce decisions carefully | Chief Legal Officer / HR | Open
R-23 | 2025-12-16 | Adverse media coverage amplifying customer churn during any integration stumble | Any operational misstep (outage, data error, fraud) during integration is likely to receive outsized media attention given the deal's public profile | Negative press coverage accelerating customer attrition and reducing investor confidence | Brand damage, accelerated customer churn, and share price pressure | 5 | 6 | 30 | M | Establish integration communications war room; prepare media response protocols for likely scenarios; engage proactive investor relations strategy | Chief Communications Officer / Investor Relations | Open
R-24 | 2025-12-16 | Mis-selling or product suitability complaints from PC Financial customers | PC Financial customers migrating to EQB products may be directed toward products unsuitable for their financial situation | Regulatory complaints to FCAC and reputational damage from suitability failures | Regulatory fines, customer remediation costs, and reputational harm | 3 | 6 | 18 | L | Implement suitability assessment protocols for customer migration; train front-line staff on product suitability standards; audit cross-sell recommendations post-close | Chief Compliance Officer / Customer Experience | Open
R-25 | 2025-12-16 | Technology vendor lock-in EQB inherits legacy PC Financial contracts expensive to exit | PC Financial holds legacy technology vendor contracts with high exit penalties or unfavorable terms that transfer to EQB post-close | Constrained technology modernization options and elevated vendor costs post-close | Higher-than-projected ongoing IT costs and strategic inflexibility in technology roadmap | 5 | 4 | 20 | L | Conduct full vendor contract audit in due diligence; negotiate exit clauses pre-close; develop technology consolidation roadmap | Chief Technology Officer / Vendor Management | Open
R-26 | 2025-12-16 | Failure to achieve $30M annual cost synergy targets | Integration complexity, vendor lock-in, HR retention costs, and operational challenges may prevent realization of projected synergies on schedule | Lower than projected EPS accretion, requiring revised investor guidance | Investor confidence erosion, share price pressure, and management credibility risk | 7 | 6 | 42 | M | Establish synergy tracking dashboard; assign accountable owners per synergy stream; tie executive compensation to synergy delivery milestones | Chief Financial Officer / Strategy | Open
R-27 | 2025-12-16 | AML compliance gaps PC Financial anti-money laundering controls not meeting EQB standards | PC Financial's AML controls and transaction monitoring systems may not meet EQB's standards or FINTRAC requirements at the point of integration | AML violations, FINTRAC sanctions, and mandatory remediation programs | Regulatory fines, reputational harm, and operational disruption during remediation | 3 | 8 | 24 | M | Conduct AML gap assessment pre-close; implement unified transaction monitoring platform; train PC Financial staff on EQB AML policies within 60 days of close | Chief Compliance Officer / AML Officer | Open
R-28 | 2025-12-16 | Change management fatigue internal teams overwhelmed by integration workstream volume | EQB is a mid-sized institution taking on a large-scale integration; internal teams may be stretched across too many simultaneous workstreams | Missed integration milestones, quality degradation, and employee burnout | Integration delays, elevated error rates, and talent attrition among EQB's own high performers | 7 | 4 | 28 | M | Establish a dedicated integration management office (IMO); hire integration specialists; limit concurrent workstreams to manageable numbers; implement milestone governance | Chief Operating Officer / Integration PMO | Open
R-29 | 2025-12-16 | ESG / reputational risk environmental or social controversy attracting scrutiny during deal | Any ESG-related controversy involving Loblaw (e.g., grocery pricing investigations) may attract scrutiny to EQB by association during the deal | Reputational damage by association and investor ESG rating pressure on EQB | ESG rating downgrades, institutional investor concern, and reputational harm | 5 | 4 | 20 | L | Establish clear public messaging on EQB's independence from Loblaw's ESG controversies; proactively communicate EQB's own ESG commitments | Chief Communications Officer / ESG | Open
R-30 | 2025-12-16 | Underestimating IT infrastructure age legacy PC Financial systems more outdated than assessed | PC Financial's legacy banking systems may be more technically outdated than disclosed in due diligence, requiring more extensive and costly modernization | Higher-than-budgeted technology remediation costs and longer integration timelines | Cost overruns, delayed synergy realization, and operational risk from running aging systems longer than planned | 5 | 6 | 30 | M | Commission independent technical due diligence on PC Financial IT infrastructure; build IT contingency budget of 20%+; develop phased modernization roadmap | Chief Technology Officer / Integration PMO | Open
R-31 | 2025-12-16 | Loss of PC Optimum co-branding benefits due to loyalty program integration complexities | Separating PC Financial from the PC Optimum loyalty ecosystem may reduce the value proposition that originally attracted PC Financial customers | Customer dissatisfaction and attrition as PC Optimum-linked banking benefits disappear post-rebrand | Accelerated customer churn and reduced cross-sell opportunity from the acquired customer base | 7 | 6 | 42 | M | Negotiate ongoing PC Optimum data access agreement with Loblaw; develop EQB-native loyalty or rewards program as substitute; phase out PC Optimum branding gradually | Chief Marketing Officer / Partnerships | Open
R-32 | 2025-12-16 | Geopolitical or macro shock recession or housing market crash affecting EQB's mortgage-heavy book | A macroeconomic downturn or housing market correction would disproportionately impact EQB's mortgage-heavy combined portfolio | Elevated mortgage defaults, increased provisions, and reduced portfolio valuations | Material financial losses, capital adequacy pressure, and impaired deal economics | 3 | 9 | 27 | M | Stress-test combined mortgage portfolio under severe macro scenarios; maintain conservative loan-to-value ratios; diversify product mix to reduce mortgage concentration | Chief Risk Officer / Credit Risk | Open
R-33 | 2025-12-16 | Insurance and indemnity gaps reps and warranties coverage insufficient for undisclosed liabilities | Standard reps and warranties insurance may not fully cover all undisclosed liabilities in PC Financial's balance sheet | EQB bears uninsured financial exposure for undisclosed liabilities surfacing post-close | Unexpected financial losses and potential litigation with Loblaw over undisclosed liabilities | 3 | 6 | 18 | L | Negotiate comprehensive reps and warranties coverage; engage M&A counsel to expand indemnity scope; establish escrow arrangements for high-risk liability categories | Chief Legal Officer / M&A Advisory | Open
R-34 | 2025-12-16 | Governance integration lag PC Financial board and committee structures not dissolved cleanly | PC Financial's existing board and governance structures may not be wound down efficiently post-close, creating ambiguity in decision-making authority | Governance confusion, delayed decisions, and potential for conflicting board-level direction during integration | Corporate governance failure, regulatory concern, and integration delays from unresolved governance structures | 3 | 4 | 12 | L | Establish clear governance wind-down timeline pre-close; define integrated governance structure on day one; engage OSC-aligned governance counsel | Board Governance Committee / General Counsel | Open
R-35 | 2025-12-16 | AI-driven personalization producing biased or discriminatory outcomes | EQB's use of PC Optimum spending data and AI models for credit and cross-sell decisions may embed biases against protected groups under the Canadian Human Rights Act | Discriminatory lending or product targeting outcomes affecting certain customer segments | Regulatory sanctions from FCAC or OSFI, reputational damage, and potential class-action liability | 3 | 6 | 18 | L | Conduct AI bias audit pre-deployment; implement fairness constraints in models; establish human-in-the-loop review for AI-driven credit decisions; document model governance | Chief Data Officer / Compliance | Open
R-36 | 2025-12-16 | TDH-EQB Fabric analytics platform fails to scale to 3.5M customers | EQB's analytics infrastructure built on Microsoft Fabric may not scale to handle data volume from 3.5M PC Financial customers without significant re-engineering | Analytics and personalization capabilities degrade, reducing effectiveness of cross-sell targeting | Reduced AI-driven revenue uplift, delayed cross-sell strategy, and elevated technology costs | 3 | 6 | 18 | L | Conduct load testing and scalability assessment of Fabric platform pre-integration; engage Microsoft Fabric specialists; build phased data onboarding plan | Chief Data Officer / Technology | Open
R-37 | 2025-12-16 | EQB credit rating downgrade due to acquisition leverage | The financial leverage taken on to fund the PC Financial acquisition may prompt credit rating agencies (DBRS Morningstar, S&P) to downgrade EQB's credit rating | Higher borrowing costs, reduced access to capital markets, and investor concern over EQB's financial position | Increased funding costs, potential covenant breaches, and share price pressure | 3 | 8 | 24 | M | Maintain conservative leverage ratios post-close; communicate deleveraging roadmap to rating agencies; build strong capital generation plan to accelerate debt repayment | Chief Financial Officer / Capital Markets | Open
R-38 | 2025-12-16 | Cross-sell conversion opportunity PC Financial credit-card-only customers convert to full EQ Bank relationships | EQB's high-interest savings and mortgage products paired with PC Optimum data-driven targeting could drive above-forecast cross-sell uptake among 3.5M customers | Accelerated deposit growth, higher revenue per customer, and stronger-than-projected EPS accretion | (POSITIVE RISK) Faster payback on acquisition cost, strengthened market position, and potential to expand synergy targets | 9 | 9 | 81 | H | Invest in AI personalization infrastructure; build seamless onboarding flows for PC Financial customers into EQB products; track cross-sell KPIs monthly post-close | Chief Revenue Officer / Digital Banking | Open
R-39 | 2025-12-16 | Omnichannel expansion opportunity Loblaw retail network opens new customer segments for EQB | EQB gains access to ~2,500 Loblaw kiosk locations and 20M+ PC Optimum members, providing a distribution channel previously unavailable to a digital-first bank | Accelerated new customer acquisition across demographic segments not typically reached through digital channels | (POSITIVE RISK) Expanded total addressable market, increased brand awareness, and stronger deposit inflows | 7 | 8 | 56 | H | Invest in in-store banking experience at Loblaw kiosks; develop targeted marketing for non-digital customer segments; track new customer acquisition from in-store channel monthly | Chief Revenue Officer / Retail Banking | Open
R-40 | 2025-12-16 | AI personalization opportunity PC Optimum spending data drives above-forecast revenue growth | PC Optimum's rich transaction-level spending data enables EQB to build AI-driven personalization capabilities that competitors lack, enabling hyper-targeted product recommendations | Above-forecast revenue from targeted cross-sell and upsell, reducing customer acquisition costs | (POSITIVE RISK) Sustainable competitive advantage from data moat, higher lifetime customer value, and potential to license analytics capabilities | 7 | 8 | 56 | H | Build proprietary AI personalization engine using PC Optimum data; establish data governance framework; invest in data science talent; protect data moat through regulatory compliance | Chief Data Officer / Revenue | Open