## Conservative
Probability of Occurrence
Very Unlikely | 1
Somewhat unlikely | 3
50-50 possibility | 5
Somewhat likely | 7
Very likely | 9
Impact of Risk : defined as the impact to the firm before the controls. (Inherent risk) |  | Financial: Possibility of a significant monetary loss or gain | Operational | Competitive Risks: Some competitors in the industry might hurt the company's business. Pick hospitals that are closed to competitors' health center, count the total admissions change rates in these hospitals. | Reputational: May impact the company brand or standing associated with a positive or negative incident/issue | Technical | Legal/Compliance
Very Low | 1
Somewhat Low | 2
Moderate | 4
Somewhat High | 6
High | 8
Extremely High | 9
EQB Inc. / PC Financial Acquisition Risk Scoring Table (Ex-Ante, as of December 16, 2025)
Risk # | Risk Description | Risk Category | Likelihood Score | Likelihood Label | Impact Score | Impact Label | Risk Score (L × I) | Priority (H/M/L) | Threshold Range
R-01 | Cybersecurity breach during IT system integration | Operational / Cyber | 9 | Very Likely | 9 | Extremely High | 81 | H | High (≥45)
R-02 | Regulatory approval delay by OSFI / Minister of Finance | Regulatory | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-03 | Customer attrition from PC Financial portfolio post-migration | Strategic / Customer | 7 | Somewhat Likely | 8 | High | 56 | H | High (≥45)
R-04 | Data migration failure or corruption of customer records and transaction history | Operational / Technical | 3 | Somewhat Unlikely | 9 | Extremely High | 27 | M | Medium (21–44)
R-05 | Key talent loss PC Financial staff exit during transition uncertainty | Operational / HR | 9 | Very Likely | 4 | Moderate | 36 | M | Medium (21–44)
R-06 | Brand confusion / reputational damage during PC Financial rebrand to EQ Bank | Reputational | 7 | Somewhat Likely | 6 | Somewhat High | 42 | M | Medium (21–44)
R-07 | Integration cost overrun beyond the $105M budget | Financial | 7 | Somewhat Likely | 6 | Somewhat High | 42 | M | Medium (21–44)
R-08 | Loblaw co-dependency disruption operational complexity of exiting Loblaw store infrastructure | Operational / Strategic | 5 | 50-50 Possibility | 8 | High | 40 | M | Medium (21–44)
R-09 | Cross-sell conversion failure EQB fails to upsell PC Financial customers into EQB products | Strategic / Revenue | 5 | 50-50 Possibility | 8 | High | 40 | M | Medium (21–44)
R-10 | Interest rate sensitivity affecting mortgage portfolio profitability post-acquisition | Financial / Market | 5 | 50-50 Possibility | 8 | High | 40 | M | Medium (21–44)
R-11 | Regulatory capital requirement changes OSFI imposes new capital buffers on combined entity | Regulatory / Capital | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-12 | Third-party vendor / contract disputes Loblaw-side service agreements not transferring cleanly | Operational / Legal | 5 | 50-50 Possibility | 6 | Somewhat High | 30 | M | Medium (21–44)
R-13 | Credit quality deterioration PC Financial loan book has higher default risk than disclosed | Financial / Credit | 5 | 50-50 Possibility | 8 | High | 40 | M | Medium (21–44)
R-14 | PIPEDA / privacy compliance failure due to expanded data migration scope | Legal / Compliance | 7 | Somewhat Likely | 8 | High | 56 | H | High (≥45)
R-15 | Competitive poaching of PC Financial customers by Big Six or fintechs during transition | Strategic / Competitive | 7 | Somewhat Likely | 6 | Somewhat High | 42 | M | Medium (21–44)
R-16 | Operational downtime during system cutover | Operational / Technical | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-17 | Fraud spike during transition account takeover and identity fraud exploiting integration confusion | Operational / Fraud | 9 | Very Likely | 6 | Somewhat High | 54 | H | High (≥45)
R-18 | Inaccurate due diligence hidden non-performing loans surfacing post-close | Financial / Credit | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-19 | HR integration friction misaligned compensation, benefits, and culture between two firms | Operational / HR | 7 | Somewhat Likely | 4 | Moderate | 28 | M | Medium (21–44)
R-20 | Liquidity risk from deposit runoff unexpected withdrawal surge if customer confidence wavers | Financial / Liquidity | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-21 | Loblaw relationship souring residual commercial dependencies create ongoing negotiation friction | Operational / Legal | 5 | 50-50 Possibility | 6 | Somewhat High | 30 | M | Medium (21–44)
R-22 | Legal challenges from PC Financial employees wrongful dismissal or class actions during integration | Legal / HR | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-23 | Adverse media coverage amplifying customer churn during any integration stumble | Reputational | 5 | 50-50 Possibility | 6 | Somewhat High | 30 | M | Medium (21–44)
R-24 | Mis-selling or product suitability complaints from PC Financial customers | Legal / Compliance | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-25 | Technology vendor lock-in EQB inherits legacy PC Financial contracts expensive to exit | Operational / Technology | 5 | 50-50 Possibility | 4 | Moderate | 20 | L | Low (≤20)
R-26 | Failure to achieve $30M annual cost synergy targets | Strategic / Financial | 7 | Somewhat Likely | 6 | Somewhat High | 42 | M | Medium (21–44)
R-27 | AML compliance gaps PC Financial anti-money laundering controls not meeting EQB standards | Legal / Compliance | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-28 | Change management fatigue internal teams overwhelmed by integration workstream volume | Operational / HR | 7 | Somewhat Likely | 4 | Moderate | 28 | M | Medium (21–44)
R-29 | ESG / reputational risk environmental or social controversy attracting scrutiny during deal | Reputational / ESG | 5 | 50-50 Possibility | 4 | Moderate | 20 | L | Low (≤20)
R-30 | Underestimating IT infrastructure age legacy PC Financial systems more outdated than assessed | Operational / Technology | 5 | 50-50 Possibility | 6 | Somewhat High | 30 | M | Medium (21–44)
R-31 | Loss of PC Optimum co-branding benefits due to loyalty program integration complexities | Strategic / Customer | 7 | Somewhat Likely | 6 | Somewhat High | 42 | M | Medium (21–44)
R-32 | Geopolitical or macro shock recession or housing market crash affecting EQB's mortgage-heavy book | Financial / Market | 3 | Somewhat Unlikely | 9 | Extremely High | 27 | M | Medium (21–44)
R-33 | Insurance and indemnity gaps reps and warranties coverage insufficient for undisclosed liabilities | Legal / Financial | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-34 | Governance integration lag PC Financial board and committee structures not dissolved cleanly | Governance | 3 | Somewhat Unlikely | 4 | Moderate | 12 | L | Low (≤20)
R-35 | AI-driven personalization producing biased or discriminatory outcomes | Legal / Technology | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-36 | TDH-EQB Fabric analytics platform fails to scale to 3.5M customers | Operational / Technology | 3 | Somewhat Unlikely | 6 | Somewhat High | 18 | L | Low (≤20)
R-37 | EQB credit rating downgrade due to acquisition leverage | Financial / Credit | 3 | Somewhat Unlikely | 8 | High | 24 | M | Medium (21–44)
R-38 | Cross-sell conversion opportunity PC Financial credit-card-only customers convert to full EQ Bank relationships | Strategic (Opportunity) | 9 | Very Likely | 9 | Extremely High | 81 | H | High (≥45)
R-39 | Omnichannel expansion opportunity Loblaw retail network opens new customer segments for EQB | Strategic (Opportunity) | 7 | Somewhat Likely | 8 | High | 56 | H | High (≥45)
R-40 | AI personalization opportunity PC Optimum spending data drives above-forecast revenue growth | Strategic (Opportunity) | 7 | Somewhat Likely | 8 | High | 56 | H | High (≥45)
Threshold Legend:
High Risk | Score ≥ 45
Medium Risk | Score 21–44
Low Risk | Score ≤ 20

## Heat Map
EQB Inc. / PC Financial Acquisition — Risk Heat Map (Ex-Ante, December 2025)
Scoring Scale: Likelihood (1/3/5/7/9) × Impact (1/2/4/6/8/9) ¦ High ≥ 45 ¦ Medium 21–44 ¦ Low ≤ 20 ¦ ★ = Positive Risk
Likelihood ↓ / Impact → |  | IMPACT SCORE →
|  | 1 Very Low | 2 Somewhat Low | 4 Moderate | 6 Somewhat High | 8 High | 9 Extremely High
LIKELIHOOD SCORE ↓ | 9 Very Likely | Score: 9 | Score: 18 | Score: 36 R-05 | Score: 54 R-17 | Score: 72 | Score: 81 R-01 ★R-38
| 7 Somewhat Likely | Score: 7 | Score: 14 | Score: 28 R-19 R-28 | Score: 42 R-06 R-07 R-15 R-26 R-31 | Score: 56 R-03 R-14 ★R-39 ★R-40 | Score: 63
| 5 50-50 | Score: 5 | Score: 10 | Score: 20 R-25 R-29 | Score: 30 R-12 R-21 R-23 R-30 | Score: 40 R-08 R-09 R-10 R-13 | Score: 45
| 3 Somewhat Unlikely | Score: 3 | Score: 6 | Score: 12 R-34 | Score: 18 R-16 R-22 R-24 R-33 R-35 R-36 | Score: 24 R-02 R-11 R-18 R-20 R-27 R-37 | Score: 27 R-04 R-32
| 1 Very Unlikely | Score: 1 | Score: 2 | Score: 4 | Score: 6 | Score: 8 | Score: 9
LEGEND
High Risk (Score ≥ 45)
Medium Risk (Score 21–44)
Low Risk (Score ≤ 20)
★ = Positive Risk — R-38, R-39, R-40